## Complete Patient Test
| Document Number | PRC-017
| Document Revision | 00
Pain Clinical Application and Web Portal Verification
Test Procedure | Expected Results | Pass/Fail | Initials | Date | Notes
Patient Enrollment and Tablet Assignment on Web Portal and Tablet
Complete Web Phase 0 tab | Patient enrolls, you are provided a new patient id | Pass | BM | 2020-06-23 09:08
Verify you completed Android Phase 0 Setup Tab | Tablet is setup and ready for the trial | Pass | BM | 2020-06-23 09:08
Verify you completed Complete Web and Android Refresh Meds Tab as part of Android Phase 0 Setup Tab | Updates to patient meds on web server are reflected in the app | Pass | BM | 2020-06-23 09:08
Android Phase 0 At Home
Complete Android Phase 0 at Home Tab | Evening logs completed and patient ready to move to phase 1 | Pass | BM | 2020-06-23 09:08
Day 1 Visit on Web Portal and Tablet
Complete Web Day 1 | Day 1 visit complete | Pass | BM | 2020-06-23 09:08
Verify you completed Android Phase 1 Setup tab | Mask assigned to tablet, patient forms completed | Pass | BM | 2020-06-23 09:08
Complete Android Phase 1 at Home tab | Phase 1 at home completes | Pass | BM | 2020-06-23 09:08
Patient Support Request on Tablet
Complete Patient Support Requests Tab | Patient Support Requests Tab complete | Pass | BM | 2020-06-23 09:08
Day 14 Visit on Web Portal
Complete Web and Tablet Day 14 Tab | Evening Log and Surveys complete | Pass | BM | 2020-06-23 09:08
Day 28 Visit on Web Portal and Tablet
Complete Web and Table Day 28 Tab | Surveys complete | Pass | BM | 2020-06-23 09:08
Complete Android Phase 2 at Home tab | Successfull complete phase 2 | Pass | BM | 2020-06-23 09:08
Complete Android Medical System Usage and Web Check tab | Android Medical System Usage and Web Check completes | Pass | BM | 2020-06-23 09:08
Day 56 Visit on Web Portal
Complete Web Day 56 Visit Tab | Day 56 Web visit complete | Pass | BM | 2020-06-23 09:10
Day 112 Visit on Web Portal
Complete Web Day 112 Visit Tab | Day 112 Web visit complete | Pass | BM | 2020-06-23 09:10
Day 196 Visit on Web Portal and Tablet
Complete Web and Tablet Day 196 Tab | Visit completes | Pass | BM | 2020-05-29 13:57
Tablet & Mask Reassignment on Tablet and Mask
Complete Tablet & Mask Reassignment Tab | Tablet & Mask Reassignment Complete | Pass | BM | 2020-05-30 15:01
Patient Record Data Updates on Web Portal
Complete Patient Record Data Updates tab | Patient Record Data Updates tab complete | Pass | BM | 2020-05-29 13:57
Patient Exclude / Unexclude, Call, Adverse Event Reporting and PI role Adverse Events, Lock and Unlock on Web Portal
Complete Call,Lock,Exclude,w PI role Tab | Call,Lock,Exclude,w/ PIrole tab complete | Pass | BM | 2020-05-29 14:34
Formulas:
Date = IF([Initials]<>"",IF([Date]<>"",[Date],NOW()),"")

## Web Phase 0
| Document Number | PRC-017
| Document Revision | 00
Pain Clinical Application and Web Portal Verification
Test Procedure | Expected Results | Pass/Fail | Initials | Date | Notes
Enroll New Patient on Web Portal
Login | Home screen displayed | Pass | BM | 2025-07-30 15:56
From the Home screen click Enroll Patient button | Patient Profile form displayed | Pass | BM | 2025-07-30 15:56
Enter 8 digit patient ID into field following the format "726-00-XXX" | Form shows Patient ID | Pass | BM | 2025-07-30 15:56
Enter 10 digit patient phone number into field | Form shows Phone Number | Pass | BM | 2025-07-30 15:56
Enter random email address into field | Form shows email address | Pass | BM | 2025-07-30 15:56
Enter Consent Date from drop down menu | Form shows selected Consent Date | Pass | BM | 2025-07-30 15:56
Enter Enrollment Date from drop down menu | Form shows selected Enrollment Date | Pass | BM | 2025-07-30 15:56
Enter patient Age of 33 into field | Form shows Age must be between 18 and 100 | Pass | BM | 2025-07-30 15:56
Select "Male" for Gender from dropdown menu | Form shows selected Gender | Pass | BM | 2025-07-30 15:56
Select "Asian' for the select dropdown menu | Form shows Asian | Pass | BM | 2025-07-30 15:56
Click Continue button | Medical History form displayed | Pass | BM | 2025-07-30 15:56
Medical History
Enter "Baseline medical history" into Patient Medical History field | Form shows Baseline medical history | Pass | BM | 2025-07-30 15:56
Click Continue button | Medications form displayed | Pass | BM | 2025-07-30 15:56
Medications
Click New Medication button | Add Medication modal displayed | Pass | BM | 2025-07-30 15:56
Type oxy in active ingredient in Active Ingredient field and a list to select from will appear. Select Oxycodone | Form shows selected Active Ingredient | Pass | BM | 2025-07-30 15:56
Select "Check if Mg per dose currently unknown" | Mg Per Dose field hidden and check box selected | Pass | BM | 2025-07-30 15:56
Unselect "Check if Mg per dose currently unknown" | Mg Per Dose field unhidden | Pass | BM | 2025-07-30 15:56
Enter "100" quantity for the Mg per dose field | Form shows Mg Per Dose and "Check if Mg per dose currently unknown." box hidden | Pass | BM | 2025-07-30 15:56
Enter "2" quantity in the Dose Per Day field | Form shows Dose Per Day | Pass | BM | 2025-07-30 15:56
Select "Capsule" for Dose form from dropdown menu | Form shows selected Dose form (check "patch" is an option but do not select) | Pass | BM | 2025-07-30 15:56
Select "Scheduled" for Regimen from dropdown menu | Check box selected | Pass | BM | 2025-07-30 15:56
Select "Check if medication prescribed in response to adverse Event" | Check box selected | Pass | BM | 2025-07-30 15:56
Enter "Test" into Patient Medication Notes field | Form shows Patient Medication Notes | Pass | BM | 2025-07-30 15:56
Click Add Medication button | The entered medication displayed on Medications form | Pass | BM | 2025-07-30 15:56
Click New Medication and add another medication using the following data: Active Ingredient = Tylenol Mg Per Dose = 200 Doses per day = 20 Dose form = Tablet Regimen = As Needed Leave box unchecked Leave Notes box empty Click Add Medication Button | Medication added and appears in table | Pass | BM | 2025-07-30 15:56
Click Continue button | Verify Patient Data Page Displayed | Pass | BM | 2025-07-30 15:56
Verify Patient Data
Select data acknowledgement | Check box selected and Continue button appears | Pass | BM | 2025-07-30 15:56
Click Continue button | Electronically Sign Records modal displayed | Pass | BM | 2025-07-30 15:56
Electronically Sign Records
Verify Name = "Jane Doe" or current user name | Name = "Jane Doe" or current user name | Pass | BM | 2025-07-30 15:56
Verify Meaning = "Patient medical data from visit Enroll New Patient" | Meaning = "Patient medical data from visit Enroll New Patient" | Pass | BM | 2025-07-30 15:56
Enter Password in field | Field shows asterisk for entry | Pass | BM | 2025-07-30 15:56
Click Electronically Sign button | Tablet assignment displayed | Pass | BM | 2025-07-30 15:56
Complete Android Phase 0 Setup
Complete Android Phase 0 Setup | Surveys completed and cards are enabled on home page one at a time. Mask assigned, user able to run sessions
Go back to web portal and finish filling in Assign Mask tab
Complete Setup Stage Tab | After completing Setup Stage, return to Register Patient on Tablet Form
Click Next button after tablet is registered | Patient Successfully Assigned to Tablet screen appears and the tablet mac address of the recently assigned tablet is displayed.
Click Exit button | Home screen displayed
Patient Enrollment in the web portal complete
Formulas:
Date = IF([Initials]<>"",Now(),"")

## Android Phase 0 Setup
| Document Number | PRC-017
| Document Revision | 00
Pain Clinical Application and Web Portal Verification
Test Procedure | Expected Results | Pass/Fail | Initials | Date | Notes
Enroll New Patient on the Tablet
Open App. | Home screen displayed. Register Tablet Button (enabled) and Register Patient Button (disabled) | Pass | BM | 2025-07-30 15:56
Review text in upper left hand corner next to home icon | Text says "App Setup" | Pass | BM | 2025-07-30 15:56
Click on the Help icon | Help text for page is displayed | Pass | BM | 2025-07-30 15:56
Click Close Help icon | Help text for page is closed | Pass | BM | 2025-07-30 15:56
Click on the Settings button | Setting page is displayed. Sync data button (enabled). Register Mask button (disabled) | Pass | BM | 2025-07-30 15:56
Verify data on settings page | Tablet MAC ID: Actual Tablet Mac ID Mask MAC ID: Not Assigned Last Sync: Last Sync Blank Patient Registration Complete: No Internet Connection: Yes Tablet Bluetooth: Yes Patient Data on Tablet: No Patient Data on Mask: No | Pass | BM | 2025-07-30 15:56
Click Home button on Navigation Menu | Home screen displayed. Register Tablet Button (enabled) and Register Patient Button (disabled) | Pass | BM | 2025-07-30 15:56
Click the Register Tablet button | Register Tablet screen displayed. Next button is (enabled) | Pass | BM | 2025-07-30 15:56
Verify Register Tablet checks have passed | Tablet connected to internet - passed Tablet connected to database - passed | Pass | BM | 2025-07-30 15:56
Review text in upper left hand corner next to home icon | Text says "Register Tablet" | Pass | BM | 2025-07-30 15:56
Click on the Help icon | Help text for page is displayed | Pass | BM | 2025-07-30 15:56
Click Close Help icon | Help text for page is closed | Pass | BM | 2025-07-30 15:56
Click on Home icon in top left corner | Confirm Exit screen is displayed | Pass | BM | 2025-07-30 15:56
Click Cancel button | Register Tablet screen displayed. Next button is (enabled) | Pass | BM | 2025-07-30 15:56
Click Next Button | Create Account screen displayed. Previous button is (enabled). Create Account button is (enabled). | Pass | BM | 2025-07-30 15:56
Click the Previous button | Register Tablet screen displayed. Next button is (enabled) | Pass | BM | 2025-07-30 15:56
Click Next Button | Create Account screen displayed. Previous button is (enabled). Create Account button is (enabled). | Pass | BM | 2025-07-30 15:56
Click on the Help icon | Help text for page is displayed | Pass | BM | 2025-07-30 15:56
Click Close Help icon | Help text for page is closed | Pass | BM | 2025-07-30 15:56
Click on Home icon in top left corner | Confirm Exit screen is displayed | Pass | BM | 2025-07-30 15:56
Click Cancel button | Create Account screen displayed. Previous button is (enabled). Create Account button is (enabled). | Pass | BM | 2025-07-30 15:56
Click Create Account Button | Tablet Registration Complete button displayed. Done button (enabled) | Pass | BM | 2025-07-30 15:56
Click on the Help icon | Help text for page is displayed | Pass | BM | 2025-07-30 15:56
Click Close Help icon | Help text for page is closed | Pass | BM | 2025-07-30 15:56
Click on the Done button | Home screen displayed. Register Tablet Button (checked) and Register Patient Button (enabled) | Pass | BM | 2025-07-30 15:56
Click on the Settings button | Setting page is displayed. Sync data button (enabled). Register Mask button (disabled) | Pass | BM | 2025-07-30 15:56
Verify data on settings page | Tablet MAC ID: MAC ID Listed Mask MAC ID: Not Assigned Last Sync: Last Sync Blank Patient Registration Complete: No Internet Connection: Yes Tablet Bluetooth: Yes Patient Data on Tablet: No Patient Data on Mask: No | Pass | BM | 2025-07-30 15:56
Click Home button on Navigation Menu | Home screen displayed. Register Tablet Button (disabled) and Register Patient Button (enabled) | Pass | BM | 2025-07-30 15:56
Review text in upper left hand corner next to home icon | Text says "App Setup" | Pass | BM | 2025-07-30 15:56
Click on the Help icon | Help text for page is displayed | Pass | BM | 2025-07-30 15:56
Click Close Help icon | Help text for page is closed | Pass | BM | 2025-07-30 15:56
Click Register Patient Button | Register Patient screen displayed. Next button (enabled) | Pass | BM | 2025-07-30 15:56
Verify Register Patient checks have passed | Tablet connected to internet - passed Tablet connected to database - passed Patient has completed enrollment process - flagged | Pass | BM | 2025-07-30 15:56
Review text in upper left hand corner next to home icon | Text says "Register Patient" | Pass | BM | 2025-07-30 15:56
Click on the Help icon | Help text for page is displayed | Pass | BM | 2025-07-30 15:56
Click Close Help icon | Help text for page is closed | Pass | BM | 2025-07-30 15:56
Click on Home icon in top left corner | Confirm Exit screen is displayed | Pass | BM | 2025-07-30 15:56
Click Cancel button | Register Patient screen displayed. Next button (enabled) | Pass | BM | 2025-07-30 15:56
Click Next button | Enter Patient Code screen displayed. Previous button (enabled). Next button (enabled) | Pass | BM | 2025-07-30 15:56
Click on the Help icon | Help text for page is displayed | Pass | BM | 2025-07-30 15:56
Click Close Help icon | Help text for page is closed | Pass | BM | 2025-07-30 15:56
Click on Home icon in top left corner | Confirm Exit screen is displayed | Pass | BM | 2025-07-30 15:56
Click Cancel button | Enter Patient Code screen displayed. Previous button (enabled). Next button (enabled) | Pass | BM | 2025-07-30 15:56
Enter Patient Code "GET CODE FROM WEB APP" | Patient Code entered is displayed in the textbox. Previous button (enabled). Next button (enabled) | Pass | BM | 2025-07-30 15:56
Click the Next button | Display Error Invalid Patient Code. Previous button (enabled), Next button (enabled) | Pass | BM | 2025-07-30 15:56
Enter Patient Code shown on web portal | Patient Code entered is displayed in the textbox. Previous button (enabled). Next button (enabled) | Pass | BM | 2025-07-30 15:56
Click the Next button | Patient Registration Complete page is displayed. Done button (enabled) | Pass | BM | 2025-07-30 15:56
Click on the Help icon | Help text for page is displayed | Pass | BM | 2025-07-30 15:56
Click Close Help icon | Help text for page is closed | Pass | BM | 2025-07-30 15:56
Click Done button | Displayed: Actions: Morning Log (enabled), Evening Log (enabled) Surveys: GAD-7 (enabled), PHQ-9 (disabled), PSQI (disabled), BPI (disabled), FIQR (disabled) | Pass | BM | 2025-07-30 15:56
Click on the Settings button | Setting page is displayed. Sync data button (enabled). Register Mask button (disabled) | Pass | BM | 2025-07-30 15:56
Verify data on settings page | Tablet MAC ID: MAC ID Listed Mask MAC ID: Not Registered Last Sync: Last Sync Date and Time Listed Patient Registration Complete: Yes Internet Connection: Yes Tablet Bluetooth: Yes Patient Data on Tablet: No Patient Data on Mask: No | Pass | BM | 2025-07-30 15:56
Click Home button on Navigation Menu | Baseline Home screen displayed | Pass | BM | 2025-07-30 15:56
Verify home page | Displayed: Actions: Morning Log (enabled), Evening Log (enabled) Surveys: GAD-7 (enabled), PHQ-9 (disabled), PSQI (disabled), BPI (disabled), FIQR (disabled) | Pass | BM | 2025-07-30 15:56
Demo Morning and EveningLogs
Select Morning log and complete using the following data: Sleep VAS = click along line to set the value somewhere close to 10 Pain VAS = click along line to set the value somewhere close to 90 Notes = blank | Displayed: Actions: Morning Log (completed), Evening Log (enabled) Surveys: GAD-7 (enabled), PHQ-9 (disabled), PSQI (disabled), BPI (disabled), FIQR (disabled) | Pass | BM | 2025-07-30 15:56
Complete Web and Android Refresh Meds Tab | Medications updated in web portal and Evening Log tested to ensure we can refresh medications from the web portal.
Select Evening log and complete using the following data: Pain VAS = click along line to set the value somewhere close to 90 Regularly Scheduled Medications Log = 3 As Needed Medications Log = 1 Notes = blank | Displayed: Actions: Morning Log (completed), Evening Log (disabled) Surveys: GAD-7 (enabled), PHQ-9 (disabled), PSQI (disabled), BPI (disabled), FIQR (disabled) | Pass | BM | 2025-07-30 15:56
Complete New Surveys Tab | Surveys completed and cards are enabled on home page one at a time. | Pass | BM | 2025-07-30 15:56
Android Phase 0 setup complete
Evening Log
Click Evening Log button | Complete Evening Log screen displayed. Next button (enabled).
Review text in upper left hand corner next of home icon | Text says "Evening Log" | Pass | BM | 2025-07-30 15:56
Click on the Help icon | Help text for page is displayed | Pass | BM | 2025-07-30 15:56
Click Close Help icon | Help text for page is closed | Pass | BM | 2025-07-30 15:56
Click on Home icon in top left corner | Confirm Exit screen is displayed | Pass | BM | 2025-07-30 15:56
Click Cancel button | Complete Evening Log screen displayed. Next button (enabled). | Pass | BM | 2025-07-30 15:56
Click the Next button | Sleep VAS screen displayed. Previous button is (enabled). Next button is (disabled) | Fail | BM | 2025-07-30 15:56 | Sleep VAS is absent
Click on the Help icon | Help text for page is displayed | Fail | BM | 2025-07-30 15:56 | Sleep VAS is absent
Click Close Help icon | Help text for page is closed | Fail | BM | 2025-07-30 15:56 | Sleep VAS is absent
Click on Home icon in top left corner | Confirm Exit screen is displayed | Fail | BM | 2025-07-30 15:56 | Sleep VAS is absent
Click Cancel button | Sleep VAS screen displayed. Previous button is (enabled). Next button is (disabled) | Fail | BM | 2025-07-30 15:56 | Sleep VAS is absent
Click along line as close to the left side as possible. You should attempt to set the value to 50 | Dot is displayed where clicked and Previous button is (enabled) and Next button is (enabled) | Fail | BM | 2025-07-30 15:56 | Sleep VAS is absent
Click the Next button | Pain VAS screen displayed. Previous button is (enabled). Next button is (disabled) | Pass | BM | 2025-07-30 15:56 | Sleep VAS is absent
Click on the Help icon | Help text for page is displayed | Pass | BM | 2025-07-30 15:56
Click Close Help icon | Help text for page is closed | Pass | BM | 2025-07-30 15:56
Click on Home icon in top left corner | Confirm Exit screen is displayed | Pass | BM | 2025-07-30 15:56
Click Cancel button | Sleep VAS screen displayed. Previous button is (enabled). Next button is (disabled) | Fail | BM | 2025-07-30 15:56 | Sleep VAS is absent
Click along line as close to the left side as possible. You should attempt to set the value to 0 | Dot is displayed where clicked and Previous button is (enabled) and Next button is (enabled) | Fail | BM | 2025-07-30 15:56 | Sleep VAS is absent
Click the Reset button | Dot is removed. Previous button is (enabled) and Next button is (disabled) | Fail | BM | 2025-07-30 15:56 | Sleep VAS is absent
Click along line as close to the right side as possible. You should attempt to set the value to 100 | Dot is displayed where clicked and Previous button is (enabled) and Next button is (enabled) | Fail | BM | 2025-07-30 15:56 | Sleep VAS is absent
Click the Reset button | Dot is removed. Previous button is (enabled) and Next button is (disabled) | Fail | BM | 2025-07-30 15:56 | Sleep VAS is absent
Click along line to set the value somewhere close to 70 | Dot is displayed where clicked and Previous button is (enabled) and Next button is (enabled) | Fail | BM | 2025-07-30 15:56 | Sleep VAS is absent
Click Next button | Regularly Scheduled Medications Log screen is displayed. Previous button (enabled). Next button is (disabled) | Pass | BM | 2025-07-30 15:56
Click on the Help icon | Help text for page is displayed | Pass | BM | 2025-07-30 15:56
Click Close Help icon | Help text for page is closed | Pass | BM | 2025-07-30 15:56
Click on Home icon in top left corner | Confirm Exit screen is displayed | Pass | BM | 2025-07-30 15:56
Click Cancel button | Regularly Scheduled Medications Log screen is displayed. Previous button (enabled). Next button is (disabled) | Pass | BM | 2025-07-30 15:56
Enter 0 for the quantity | 0 is displayed in the textbox. Previous button is (enabled), Next button is (enabled). | Pass | BM | 2025-07-30 15:56
Erase the 0 and leave the field blank. | textbox is blank. Previous button (enabled). Next button (disabled) | Pass | BM | 2025-07-30 15:56
Enter 0 for the quantity | 0 is displayed in the textbox. Previous button is (enabled), Next button is (enabled). | Pass | BM | 2025-07-30 15:56
Click Next button | As Needed Medications Log screen is displayed. Previous button (enabled). Next button is (disabled) | Pass | BM | 2025-07-30 15:56
Click Previous button | Regularly Scheduled Medications Log screen is displayed. Previous button (enabled). Next button is (enabled) | Pass | BM | 2025-07-30 15:56
Click Next button | As Needed Medications Log screen is displayed. Previous button (enabled). Next button is (disabled) | Pass | BM | 2025-07-30 15:56
Enter 0 for the quantity | 0 is displayed in the textbox. Previous button is (enabled), Next button is (enabled). | Pass | BM | 2025-07-30 15:56
Erase the 0 and leave the field blank. | textbox is blank. Previous button (enabled). Next button (disabled) | Pass | BM | 2025-07-30 15:56
Enter 0 for the quantity | 0 is displayed in the textbox. Previous button is (enabled), Next button is (enabled). | Pass | BM | 2025-07-30 15:56
Click Next button | Notes screen is displayed. Previous button (enabled), Next button (enabled) | Pass | BM | 2025-07-30 15:56
Click on the Help icon | Help text for page is displayed | Pass | BM | 2025-07-30 15:56
Click Close Help icon | Help text for page is closed | Pass | BM | 2025-07-30 15:56
Click on Home icon in top left corner | Confirm Exit screen is displayed | Failed | BM | 2025-07-30 15:56 | Notes is absent
Click Cancel button | Notes screen is displayed. Previous button (enabled), Next button (enabled) | Failed | BM | 2025-07-30 15:56 | Notes is absent
Enter "Test" in the notes field and click the Next button | Evening Log Complete screen displayed. Done button (enabled). | Pass | BM | 2025-07-30 15:56
Click on the Help icon | Help text for page is displayed | Pass | BM | 2025-07-30 15:56
Click Close Help icon | Help text for page is closed | Pass | BM | 2025-07-30 15:56
Click Done button | Baseline Home screen displayed | Pass | BM | 2025-07-30 15:56
Verify home page | Displayed: Actions: Evening Log (disabled) Surveys: GAD-7 (checked), PHQ-9 (checked), PSQI (checked), NPSI (checked) | Failed | BM | 2025-07-30 15:56 | Evening log is enabled
Enroll new patient on the tablet complete
Return to Patient Enrollment Tab to complete tablet assignment
Formulas:
Date = IF([Initials]<>"",Now(),"")

## Web and Android Refresh Meds
| Document Number | PRC-017
| Document Revision | 00
Pain Clinical Application and Web Portal Verification
Test Procedure | Expected Results | Pass/Fail | Initials | Date | Notes
Add Medication in Web Portal and Tablet
On home screen, find patient, click kebab menu and select Patient Record | Patient Adherence tab is selected and displayed
Click Medications Tab | Medications form loads and tab is white, Patient Adherence tab is green
Click Update Medications | Form updates to show current medications
Click New Medications Button | Add Medication form displayed
Add new medication using the following data: Active Ingredient = Advil Mg Per Dose = 200 Doses per day = 20 Dose form = Capsule Regimen = As Needed Leave box unchecked Leave Notes box empty Click Add Medication Button | Medication added to table
Click Save Button | Save Pain Medication Changes displayed
Enter Password in field | Field shows asterisk for entry
Enter "Medication update" in change reason and then click save changes | Form reloads to show the list of versions for these data
Return to tablet
Click Evening Log button | Complete Evening Log screen displayed. Next button (enabled).
Click the Next button | Pain VAS screen displayed. Previous button is (enabled). Next button is (disabled)
Click along line to set the value somewhere close to 70 | Dot is displayed where clicked and Previous button is (enabled) and Next button is (enabled)
Click Next button | Regularly Scheduled Medications Log screen is displayed. Previous button (enabled). Next button is (disabled)
Enter 0 for the quantity | 0 is displayed in the textbox. Previous button is (enabled), Next button is (enabled).
Click Next button | As Needed Medications Log screen is displayed. Previous button (enabled). Next button is (disabled)
Verify As Needed Medications | Advil and Tylenol should be displayed
Click on Home icon in top left corner | Confirm Exit screen is displayed
Click Exit button | Therapy Home Screen displayed
Remove Medication in Web Portal
On home screen, find patient, click kebab menu and select Patient Record | Patient Adherence tab is selected and displayed
Click Medications Tab | Medications form loads with version history and tab is white, Patient Adherence tab is green
Click Update Medications | Form updates to show current medications
For Advil, click kebab menu and select Archive | Confirm Archive screen is displayed
Click Archive | A red x icon will appear next to Advil
Click Save Button | Save Pain Medication Changes displayed
Enter Password in field | Field shows asterisk for entry
Enter "Removed Advil" in change reason and then click save changes | Form reloads to show the list of versions for these data
Return to tablet
Click Evening Log button | Complete Evening Log screen displayed. Next button (enabled).
Click the Next button | Pain VAS screen displayed. Previous button is (enabled). Next button is (disabled)
Click along line to set the value somewhere close to 70 | Dot is displayed where clicked and Previous button is (enabled) and Next button is (enabled)
Click Next button | Regularly Scheduled Medications Log screen is displayed. Previous button (enabled). Next button is (disabled)
Enter 0 for the quantity | 0 is displayed in the textbox. Previous button is (enabled), Next button is (enabled).
Click Next button | As Needed Medications Log screen is displayed. Previous button (enabled). Next button is (disabled)
Verify As Needed Medications | Tylenol should be displayed, Aleve should be hidden
Click on Home icon in top left corner | Confirm Exit screen is displayed
Click Exit button | Therapy Home Screen displayed
Refresh Meds in web portal and tablet complete

## Android Phase 0 At Home
| Document Number | PRC-017
| Document Revision | 00
Pain Clinical Application and Web Portal Verification
Test Procedure | Expected Results | Pass/Fail | Initials | Date | Notes
Phase 0 Android App Testing
Evening Log on Tablet
Set Tablet date/time to tonight at 6:00PM
Verify home page | Displayed: Actions: Morning Log (checked) Evening Log (enabled) Surveys: All Checked | Pass | BM | 2025-07-30 15:56
Select Evening log and complete using the following data: Pain VAS = click along line to set the value somewhere close to 90 Regularly Scheduled Medications Log = 3 As Needed Medications Log = 1 Notes = blank | Evening Log Complete | Pass | BM | 2025-07-30 15:56
Verify home page | Displayed: Actions: Morning Log (checked) Evening Log (checked) Surveys: All Checked Progress: Completed Evening Log: 1 of 1 days | Pass | BM | 2025-07-30 15:56
Evening Log on Tablet
Set Tablet date/time +1 day ahead at 6:00AM
Verify home page | Displayed: Actions: Morning Log (enabled) Evening Log (disabled) Surveys: (Hidden) Progress: Completed Evening Log: 1 of 2 days | Pass | BM | 2025-07-30 15:56
Evening Log on Tablet
Set Tablet date/time to 6:00PM that evening
Verify home page | Displayed: Actions: Morning Log (missed) Evening Log (enabled) Surveys: (Hidden) Progress: Completed Evening Log: 1 of 2 days | Pass | BM | 2025-07-30 15:56
Select Evening log and complete using the following data: Pain VAS = click along line to set the value somewhere close to 90 Regularly Scheduled Medications Log = 3 As Needed Medications Log = 1 Notes = blank | Evening Log Complete (confirm copy on evening log for as needed meds and record here: | Pass | BM | 2025-07-30 15:56
Verify home page | Displayed: Actions: Morning Log (missed) Evening Log (checked) Surveys: (Hidden) Progress: Completed Evening Log: 2 of 2 days | Pass | BM | 2025-07-30 15:56
Morning & Evening Log on Tablet (Day 3-10)
Set Tablet date/time +1 days ahead at 6:00am complete morning logs then set time to 6:00PM to complete Evening Logs. Repeat for days 3-10
Complete Evening log for next 8 days using the following data: Pain VAS = click along line to set the value somewhere close to 90 Regularly Scheduled Medications Log = Alternate between entering a quantity of 5 and 6 As Needed Medications Log = Alternate between entering a quantity of 3 and 4 All other fields to be entered to testers discretion. | Evening Logs complete for next consecutive 8 days | Pass | BM | 2025-07-30 15:56
Verify home page after Evening Log on day 10 | Displayed: Actions: Evening Log (checked) Surveys: (Hidden) Survey Reminder: Visible | Pass | BM | 2025-07-30 15:56
Verify home page shows the surveys are upcoming | Survey reminder shown on home screen | Pass | BM | 2025-07-30 15:56
Set tablet to day 12 at 6:00PM to complete surveys
Verify nome page shows | Displayed: Actions: Morning Log (missed), Evening Log (enabled) Surveys: GAD-7 (enabled), PHQ-9 (disabled), PSQI (disabled), BPI (disabled), FIQR (disabled) | Pass | BM | 2025-07-30 15:56
Complete New Surveys Tab | Surveys complete | Pass | BM | 2025-07-30 15:56
Android Phase 0 at Home Completed
Formulas:
Date = IF([Initials]<>"",Now(),"")

## Web Day 1
| Document Number | PRC-017
| Document Revision | 00
Pain Clinical Application and Web Portal Verification
Test Procedure | Expected Results | Pass/Fail | Initials | Date | Notes
Day 1 Visit on Web Portal
Login | Home screen displayed | Pass | BM | 2025-07-30 15:56
On home screen, find patient, click kebab menu and select Day 1 Visit | Patient Adherence screen displayed | Pass | BM | 2025-07-30 15:56
Using the data presented in the tables, ensure the Morning Logs 0 of 1 days adhered is correct | Card shows correct adherence rate | Pass | BM | 2025-07-30 15:56
Using the data presented in the tables, ensure the Evening Logs 1 of 1 days adhered is correct | Card shows correct adherence rate | Pass | BM | 2025-07-30 15:56
Using the data presented in the tables, ensure the Average Pain Vas is correct. Note its the average across both evening and morning pain vas. | Card shows correct average value | Pass | BM | 2025-07-30 15:56
Using the data presented in the tables, ensure the Average Sleep Vas is correct. Please export to excel and estimate the averages to confirm their values. | Card shows correct average value | Pass | BM | 2025-07-30 15:56
Using the data presented in the tables, ensure the calendar shows the correct adherence data for each date. | Calendar shows correct daily usage and adherence. | Pass | BM | 2025-07-30 15:56
Scroll to bottom of screen, select the acknowledgment check box in the Eligibility Criteria Review | Check box selected | Pass | BM | 2025-07-30 15:56
Click Continue button | Patient Profile screen displayed | Pass | BM | 2025-07-30 15:56
Enter new 10 digit patient phone number into field | Form shows Patient Phone Number | Pass | BM | 2025-07-30 15:56
Click Continue button | Medical History form displayed | Pass | BM | 2025-07-30 15:56
Click Previous button | Patient Profile screen displayed with updated phone number | Pass | BM | 2025-07-30 15:56
Click Continue button | Medical History form displayed | Pass | BM | 2025-07-30 15:56
Medical History
Update "Baseline Medical History" to "Day 1 Medical History" into Patient Medical History field | Form shows Day 1 Medical History | Pass | BM | 2025-07-30 15:56
Click Continue button | Medications form displayed | Pass | BM | 2025-07-30 15:56
Medications
Click New Medication button | Add Medication modal displayed | Pass | BM | 2025-07-30 15:56
Add new medication using the following data: Active Ingredient = Aleve Mg Per Dose = 100 Doses per day = 5 Dose form = Tablet Regimen = As needed Leave box unchecked Leave Notes box empty Click Add Medication Button | Medication added to table | Pass | BM | 2025-07-30 15:56
Click Continue button | Verify Patient Data Page Displayed | Pass | BM | 2025-07-30 15:56
Verify Patient Data
Click Review Profile button | Patient Data displayed | Pass | BM | 2025-07-30 15:56
Select data acknowledgement | Check box selected and Continue button appears | Pass | BM | 2025-07-30 15:56
Click Continue button | Electronically Sign Records modal displayed | Pass | BM | 2025-07-30 15:56
Electronically Sign Records
Verify Name = "Jane Doe" or current user name | Name = "Jane Doe" or current user name | Pass | BM | 2025-07-30 15:56
Verify Meaning = "Patient medical data from visit Day 1 Visit" | Meaning = Patient medical data from visit Day 1 Visit" | PAss | BM | 2025-07-30 15:56
Enter Password in field | Field shows asterisk for entry | Pass | BM | 2025-07-30 15:56
Click Electronically Sign button | Assign mask screen shows on web portal | Pass | BM | 2025-07-30 15:56
Complete Android Phase 1 Setup tab
Complete Android Phase 1 Setup tab | Surveys completed and cards are enabled on home page one at a time. Mask assigned, user able to run sessions | Pass | BM | 2025-07-30 15:56
Mask Assignment
On web portal, click Sync Mask button after tablet is registered | Assign Mask To Tablet screen displayed and the mask mac address of the recently assigned mask is displayed. | Pass | BM | 2025-07-30 15:56
Click Exit button, then provide password to finish the session. | Home screen loads | Pass | BM | 2025-07-30 15:56
Day 1 Visit in the web portal complete
Formulas:
Date = IF([Initials]<>"",Now(),"")

## Android Phase 1 Setup
| Document Number | PRC-017
| Document Revision | 00
Pain Clinical Application and Web Portal Verification
Test Procedure | Expected Results | Pass/Fail | Initials | Date | Notes
Day 1 Visit on Tablet
On tablet update the date to current time
From the Home screen click on the Settings button | Settings Screen Displayed. Sync Data button (enabled). Register Mask button (disabled) | Pass | BM | 2025-07-30 15:56
Click the Sync Data button | Register Mask button is enabled. Sync Mask Logs (displayed and enabled) | Pass | BM | 2025-07-30 15:56
Verify data on settings page | Tablet MAC ID: MAC ID Listed Mask MAC ID: Not Registered Last Sync: Last Sync Date and Time Listed Patient Registration Complete: Yes Internet Connection: Yes Tablet Bluetooth: Yes Patient Data on Tablet: No Patient Data on Mask: No | Pass | BM | 2025-07-30 15:56
Click on the Help icon | Help text for page is displayed | Pass | BM | 2025-07-30 15:56
Click Close Help icon | Help text for page is closed | Pass | BM | 2025-07-30 15:56
Click the Register Mask button | Register Mask screen is displayed. Next button (enabled) | Pass | BM | 2025-07-30 15:56
Verify Register Tablet checks have passed | Tablet connected to internet - passed Tablet connected to database - passed Tablet Bluetooth is on - passed | Pass | BM | 2025-07-30 15:56
Review text in upper left hand corner next to home icon | Text says "Assign Mask" | Pass | BM | 2025-07-30 15:56
Click on the Help icon | Help text for page is displayed | Pass | BM | 2025-07-30 15:56
Click Close Help icon | Help text for page is closed | Pass | BM | 2025-07-30 15:56
Click on Home icon in top left corner | Confirm Exit screen is displayed | Pass | BM | 2025-07-30 15:56
Click Cancel button | Register Mask screen is displayed. Next button (enabled) | Pass | BM | 2025-07-30 15:56
Click Next button | Select mask screen is displayed. Previous button (enabled). Next button (disabled) | Pass | BM | 2025-07-30 15:56
Click on the Help icon | Help text for page is displayed | Pass | BM | 2025-07-30 15:56
Click Close Help icon | Help text for page is closed | Pass | BM | 2025-07-30 15:56
Click on Home icon in top left corner | Confirm Exit screen is displayed | Pass | BM | 2025-07-30 15:56
Click Cancel button | Select mask screen is displayed. Previous button (enabled). Next button (disabled) | Pass | BM | 2025-07-30 15:56
Pickup available mask to be assigned and turn power switch to on
Select the mask from the list of available masks | Next button (enabled) | Pass | BM | 2025-07-30 15:56
Click on the Next button | Display screen Pairing Mask With Tablet. Previous and Next buttons do not appear on page. Help icon does not appear on page. | Pass | BM | 2025-07-30 15:56
Pairing Mask With Tablet completed | Mask registration complete screen displayed. Done button (enabled) | Pass | BM | 2025-07-30 15:56
Click on the Help icon | Help text for page is displayed | Pass | BM | 2025-07-30 15:56
Click Close Help icon | Help text for page is closed | Pass | BM | 2025-07-30 15:56
Click the Done button | Home screen displayed | Pass | BM | 2025-07-30 15:56
Click Settings button | Display Settings screen. Sync Data button (enabled). Register Mask button (disabled). Sync Mask Logs (enabled). | Pass | BM | 2025-07-30 15:56
Verify data on Settings screen | Tablet MAC ID: MAC ID Listed Mask MAC ID: Updated to match the newly assigned mask MAC ID Last Sync: Last Sync Date and Time Listed Patient Registration Complete: Yes Internet Connected: Yes Tablet Bluetooth: Yes Patient Data on Tablet: No Patient Data on Mask: No | Pass | BM | 2025-07-30 15:56
Click on the Home button on Navigation menu | Displayed: Actions: Evening Log (disabled), Regular Session (enabled) Surveys: Surveys: GAD-7 (enabled), PHQ-9 (disabled), PSQI (disabled), BPI (disabled), FIQR (disabled) , Completed Regular Session: 0 of 1 days, Completed End of Day Sessions 0 of 1 days Training: Watch Video, Brightness, Volume, Power On, Charging | Pass | BM | 2025-07-30 15:56
Click on Video button. | Instructional Video screen is displayed. Done button is (enabled). Video automatically begins playing | Pass | BM | 2025-07-30 15:56
Click on the Help icon | Help text for page is displayed | Pass | BM | 2025-07-30 15:56
Click Close Help icon | Help text for page is closed | Pass | BM | 2025-07-30 15:56
Review text in top left corner next to Home Icon. | Text says "Instructional Video" | Pass | BM | 2025-07-30 15:56
Watch video for 60 seconds. | Video plays normally and there are no issues with playback | Pass | BM | 2025-07-30 15:56
Click Done button | Therapy Home page screen displayed | Pass | BM | 2025-07-30 15:56
Click on Brightness button | Brightness Instructions shown | Pass | BM | 2025-07-30 15:56
Swipe up or down to close | Therapy Home page screen displayed | Pass | BM | 2025-07-30 15:56
Click on Volume button | Volume Instructions shown | Pass | BM | 2025-07-30 15:56
Swipe up or down to close | Therapy Home page screen displayed | Pass | BM | 2025-07-30 15:56
Click on Power On button | Power On Instructions shown | Pass | BM | 2025-07-30 15:56
Swipe up or down to close | Therapy Home page screen displayed | Pass | BM | 2025-07-30 15:56
Click on Charging button | Charging Instructions shown | Pass | BM | 2025-07-30 15:56
Swipe up or down to close | Therapy Home page screen displayed | Pass | BM | 2025-07-30 15:56
Patient completes surveys
Complete New Surveys Tab | Surveys completed and cards are enabled on home page one at a time. | Pass | BM | 2025-07-30 15:56
Regular Session
Click Regular Session button | Regular Session screen displayed. Next button (enabled). | Pass | BM | 2025-07-30 15:56
Review text in upper left hand corner next of home icon | Text says "Regular Therapy" | Pass | BM | 2025-07-30 15:56
Click on the Help icon | Help text for page is displayed | Pass | BM | 2025-07-30 15:56
Click Close Help icon | Help text for page is closed | Pass | BM | 2025-07-30 15:56
Click on Home icon in top left corner | Confirm Exit screen is displayed | Pass | BM | 2025-07-30 15:56
Click Cancel button | Complete Evening Log screen displayed. Next button (enabled). | Pass | BM | 2025-07-30 15:56
Click the Next button | Pain VAS screen displayed. Previous button is (enabled). Next button is (disabled) | Pass | BM | 2025-07-30 15:56
Click on the Help icon | Help text for page is displayed | Pass | BM | 2025-07-30 15:56
Click Close Help icon | Help text for page is closed | Pass | BM | 2025-07-30 15:56
Click on Home icon in top left corner | Confirm Exit screen is displayed | Pass | BM | 2025-07-30 15:56
Click Cancel button | Sleep VAS screen displayed. Previous button is (enabled). Next button is (disabled) | Pass | BM | 2025-07-30 15:56
Click along line as close to the left side as possible. You should attempt to set the value to 0 | Dot is displayed where clicked and Previous button is (enabled) and Next button is (enabled) | Pass | BM | 2025-07-30 15:56
Click the Reset button | Dot is removed. Previous button is (enabled) and Next button is (disabled) | Pass | BM | 2025-07-30 15:56
Click along line as close to the right side as possible. You should attempt to set the value to 100 | Dot is displayed where clicked and Previous button is (enabled) and Next button is (enabled) | Pass | BM | 2025-07-30 15:56
Click the Reset button | Dot is removed. Previous button is (enabled) and Next button is (disabled) | Pass | BM | 2025-07-30 15:56
Click along line to set the value somewhere close to 70 | Dot is displayed where clicked and Previous button is (enabled) and Next button is (enabled) | Pass | BM | 2025-07-30 15:56
Click Next button | Start Session screen displayed. Next button (enabled). | Pass | BM | 2025-07-30 15:56
Click on the Help icon | Help text for page is displayed | Pass | BM | 2025-07-30 15:56
Click Close Help icon | Help text for page is closed | Pass | BM | 2025-07-30 15:56
Click on Home icon in top left corner | Confirm Exit screen is displayed | Pass | BM | 2025-07-30 15:56
Click Start button. | Session Starting screen displayed. Pause Countdown button is enabled. Countdown starts from 5 to 0. | Pass | BM | 2025-07-30 15:56
Click Pause Countdown button before it reaches 0. | Countdown Pauses screen displayed. Countdown is stopped at same number displayed when Pause Countdown button was clicked. Restart Countdown button is enabled. | Pass | BM | 2025-07-30 15:56
Click on the Help icon | Help text for page is displayed | Pass | BM | 2025-07-30 15:56
Click Close Help icon | Help text for page is closed | Pass | BM | 2025-07-30 15:56
Click Restart Countdown button | Session Starting screen displayed. Pause Countdown button is enabled. Countdown resumes where it left off when Restart Countdown button was clicked. | Pass | BM | 2025-07-30 15:56
Countdown reaches 0 | Session in Progress screen is displayed. Stop Session Button (enabled). Issue with Mask button (enabled). Counter starts counting up from 1 until you press Stop Session. | Pass | BM | 2025-07-30 15:56
Click on the Help icon | Help text for page is displayed | Pass | BM | 2025-07-30 15:56
Click Close Help icon | Help text for page is closed | Pass | BM | 2025-07-30 15:56
Click Stop Session button | Exit Session screen is displayed. Return to Session button (enabled). Exit Session button (enabled) | Pass | BM | 2025-07-30 15:56
Click Return to Session button | Session in Progress screen is displayed. Stop Session Button (enabled). Issue with Mask button (enabled). Counter starts counting up from where it left off. | Pass | BM | 2025-07-30 15:56
Click Issue with mask button | Issue with Mask screen displayed. Cancel button (enabled). Continue button (enabled). | Pass | BM | 2025-07-30 15:56
Click Cancel Button | Session in Progress screen is displayed. Stop Session Button (enabled). Issue with Mask button (enabled). Counter starts counting up from where it left off. | Pass | BM | 2025-07-30 15:56
Click Stop Session button | Exit Session screen is displayed. Return to Session button (enabled). Exit Session button (enabled) | Pass | BM | 2025-07-30 15:56
Click Exit Session button | Session Complete screen displayed. Next button (enabled). | Pass | BM | 2025-07-30 15:56
Click Next button | Pain VAS screen is displayed. Next button (disabled). No dot displayed on the line. Reset button (disabled) | Pass | BM | 2025-07-30 15:56
Click on the Help icon | Help text for page is displayed | Pass | BM | 2025-07-30 15:56
Click Close Help icon | Help text for page is closed | Pass | BM | 2025-07-30 15:56
Click along line to set the value somewhere close to 30 | Dot is displayed where clicked and Previous button is (enabled) and Next button is (enabled) | Pass | BM | 2025-07-30 15:56
Click the Next button. | Regular Therapy Session complete screen displayed. Done button (enabled). | Pass | BM | 2025-07-30 15:56
Click on the Help icon | Help text for page is displayed | Pass | BM | 2025-07-30 15:56
Click Close Help icon | Help text for page is closed | Pass | BM | 2025-07-30 15:56
Click the Done button. | Home screen displayed. Evening Log (disabled). Regular Session button (enabled, 1). | Pass | BM | 2025-07-30 15:56
Android Phase 1 Setup Complete
Formulas:
Date = IF([Initials]<>"",Now(),"")

## Android Phase 1 at Home
| Document Number | PRC-017
| Document Revision | 00
Pain Clinical Application and Web Portal Verification
We have already tested the morning and evening logs. We just test Regular and End of Day sessions here
Test Procedure | Expected Results | Pass/Fail | Initials | Date | Notes
Android Phase 1 at home, set tablet to 6am the following day.
Ensure morning logs capture pain, and sleep fields | Morning log appears and captures those data. | Pass | BM | 2025-07-30 15:56
Ensure regular sessions available throughout the day. Complete the Regular Session section below. | Regular therapy sessions pass | Pass | BM | 2025-07-30 15:56
Android Phase 1 at home, set tablet to 6pm that same day
Ensure evening logs capture pain, meds fields. | Evening log appears and captures those data. | Pass | BM | 2025-07-30 15:56
Ensure end of day sessions available at night. Complete the end of day session below. | End of day therapy sessions pass | Pass | BM | 2025-07-30 15:56
Set tablet to 13 days after Day 1 visit | Confirm surveys show up and can be filled in by user | Pass | BM | 2025-07-30 15:56
Set tablet to 27 days after day 1 visit | Complete New Surveys Tab to ensure HFUE and PGIC surveys show up properly. | Pass | BM | 2025-07-30 15:56
Regular Session
Click Regular Session button | Regular Session screen displayed. Next button (enabled). | Pass | BM | 2025-07-30 15:56
Review text in upper left hand corner next of home icon | Text says "Regular Therapy" | Pass | BM | 2025-07-30 15:56
Click on the Help icon | Help text for page is displayed | Pass | BM | 2025-07-30 15:56
Click Close Help icon | Help text for page is closed | Pass | BM | 2025-07-30 15:56
Click on Home icon in top left corner | Confirm Exit screen is displayed | Pass | BM | 2025-07-30 15:56
Click Cancel button | Complete Regular Session screen displayed. Next button (enabled). | Pass | BM | 2025-07-30 15:56
Click the Next button | Sleep VAS screen displayed with no action required. Next button is (enabled). | Pass | BM | 2025-07-30 15:56
Click on the Help icon | Help text for page is displayed | Pass | BM | 2025-07-30 15:56
Click Close Help icon | Help text for page is closed | Pass | BM | 2025-07-30 15:56
Click on Home icon in top left corner | Confirm Exit screen is displayed | Pass | BM | 2025-07-30 15:56
Click Cancel button | Sleep VAS screen displayed with no action required. Next button is (enabled). | Pass | BM | 2025-07-30 15:56
Click the Next button | Pain VAS screen displayed. Previous button is (enabled). Next button is (disabled) | Pass | BM | 2025-07-30 15:56
Click on the Help icon | Help text for page is displayed | Pass | BM | 2025-07-30 15:56
Click Close Help icon | Help text for page is closed | Pass | BM | 2025-07-30 15:56
Click on Home icon in top left corner | Confirm Exit screen is displayed | Pass | BM | 2025-07-30 15:56
Click Cancel button | Sleep VAS screen displayed. Previous button is (enabled). Next button is (disabled) | Pass | BM | 2025-07-30 15:56
Click along line as close to the left side as possible. You should attempt to set the value to 0 | Dot is displayed where clicked and Previous button is (enabled) and Next button is (enabled) | Pass | BM | 2025-07-30 15:56
Click the Reset button | Dot is removed. Previous button is (enabled) and Next button is (disabled) | Pass | BM | 2025-07-30 15:56
Click along line as close to the right side as possible. You should attempt to set the value to 100 | Dot is displayed where clicked and Previous button is (enabled) and Next button is (enabled) | Pass | BM | 2025-07-30 15:56
Click the Reset button | Dot is removed. Previous button is (enabled) and Next button is (disabled) | Pass | BM | 2025-07-30 15:56
Click along line to set the value somewhere close to 70 | Dot is displayed where clicked and Previous button is (enabled) and Next button is (enabled) | Pass | BM | 2025-07-30 15:56
Click Next button | Start Session screen displayed. Next button (enabled). | Pass | BM | 2025-07-30 15:56
Click on the Help icon | Help text for page is displayed | Pass | BM | 2025-07-30 15:56
Click Close Help icon | Help text for page is closed | Pass | BM | 2025-07-30 15:56
Click on Home icon in top left corner | Confirm Exit screen is displayed | Pass | BM | 2025-07-30 15:56
Click Start button. | Session Starting screen displayed. Pause Countdown button is enabled. Countdown starts from 5 to 0. | Pass | BM | 2025-07-30 15:56
Countdown reaches 0 | Session in Progress screen is displayed. Stop Session Button (enabled). Issue with Mask button (enabled). Counter starts counting up from 1 until you press Stop Session. | Pass | BM | 2025-07-30 15:56
Click Stop Session button | Exit Session screen is displayed. Return to Session button (enabled). Exit Session button (enabled) | Pass | BM | 2025-07-30 15:56
Click Exit Session button | Session Complete screen displayed. Next button (enabled). | Pass | BM | 2025-07-30 15:56
Click Next button | Pain VAS screen is displayed. Next button (disabled). No dot displayed on the line. Reset button (disabled) | Pass | BM | 2025-07-30 15:56
Click on the Help icon | Help text for page is displayed | Pass | BM | 2025-07-30 15:56
Click Close Help icon | Help text for page is closed | Pass | BM | 2025-07-30 15:56
Click along line to set the value somewhere close to 30 | Dot is displayed where clicked and Previous button is (enabled) and Next button is (enabled) | Pass | BM | 2025-07-30 15:56
Click the Next button. | Regular Therapy Session complete screen displayed. Done button (enabled). | Pass | BM | 2025-07-30 15:56
Click on the Help icon | Help text for page is displayed | Pass | BM | 2025-07-30 15:56
Click Close Help icon | Help text for page is closed | Pass | BM | 2025-07-30 15:56
Click the Done button. | Home screen displayed. Evening Log (enabled). Regular Session button (enabled, 2). | Pass | BM | 2025-07-30 15:56
Run another regular session and confirm you are not asked to fill in Sleep or Pain Vas | Regular session completes and you were able to skip sleep and pain vas sliders | Pass
End of Day Session
Click End of Day Session button | End of Day Session screen displayed. Next button (enabled). | Pass | BM | 2025-07-30 15:56
Review text in upper left hand corner next of home icon | Text says "End of Day Session" | Pass | BM | 2025-07-30 15:56
Click on the Help icon | Help text for page is displayed | Pass | BM | 2025-07-30 15:56
Click Close Help icon | Help text for page is closed | Pass | BM | 2025-07-30 15:56
Click on Home icon in top left corner | Confirm Exit screen is displayed | Pass | BM | 2025-07-30 15:56
Click Cancel button | Complete Evening Log screen displayed. Next button (enabled). | Pass | BM | 2025-07-30 15:56
Click the Next button | Pain VAS screen displayed. Previous button is (enabled). Next button is (disabled) | Pass | BM | 2025-07-30 15:56
Click on the Help icon | Help text for page is displayed | Pass | BM | 2025-07-30 15:56
Click Close Help icon | Help text for page is closed | Pass | BM | 2025-07-30 15:56
Click on Home icon in top left corner | Confirm Exit screen is displayed | Pass | BM | 2025-07-30 15:56
Click Cancel button | Pain VAS screen displayed. Previous button is (enabled). Next button is (disabled) | Pass | BM | 2025-07-30 15:56
Click along line as close to the left side as possible. You should attempt to set the value to 0 | Dot is displayed where clicked and Previous button is (enabled) and Next button is (enabled) | Pass | BM | 2025-07-30 15:56
Click the Reset button | Dot is removed. Previous button is (enabled) and Next button is (disabled) | Pass | BM | 2025-07-30 15:56
Click along line as close to the right side as possible. You should attempt to set the value to 100 | Dot is displayed where clicked and Previous button is (enabled) and Next button is (enabled) | Pass | BM | 2025-07-30 15:56
Click the Reset button | Dot is removed. Previous button is (enabled) and Next button is (disabled) | Pass | BM | 2025-07-30 15:56
Click along line to set the value somewhere close to 70 | Dot is displayed where clicked and Previous button is (enabled) and Next button is (enabled) | Pass | BM | 2025-07-30 15:56
Click the Next button | Start Session screen displayed. Start button (enabled). | Pass | BM | 2025-07-30 15:56
Click on the Help icon | Help text for page is displayed | Pass | BM | 2025-07-30 15:56
Click Close Help icon | Help text for page is closed | Pass | BM | 2025-07-30 15:56
Click on Home icon in top left corner | Confirm Exit screen is displayed | Pass | BM | 2025-07-30 15:56
Click Start button. | Session Starting screen displayed. Pause Countdown button is enabled. Countdown starts from 5 to 0. | Pass | BM | 2025-07-30 15:56
Countdown reaches 0 | Session in Progress screen is displayed. Stop Session Button (enabled). Issue with Mask button (enabled). Counter starts counting up from 1 until you press Stop Session. | Pass | BM | 2025-07-30 15:56
Click Stop Session button | Exit Session screen is displayed. Return to Session button (enabled). Exit Session button (enabled) | Pass | BM | 2025-07-30 15:56
Click Exit Session button | Session Complete screen displayed. Next button (enabled). | Pass | BM | 2025-07-30 15:56
Click the Next button. | End of Day Session complete screen displayed. Done button (enabled). | Pass | BM | 2025-07-30 15:56
Click on the Help icon | Help text for page is displayed | Pass | BM | 2025-07-30 15:56
Click Close Help icon | Help text for page is closed | Pass | BM | 2025-07-30 15:56
Click the Done button. | Home screen displayed. Evening Log (checked). End of Day Session (checked). Regular Session button (hidden). | Pass | BM | 2025-07-30 15:56
Return to web portal for Day 14 visit
Formulas:
Date = IF([Initials]<>"",Now(),"")

## New Surveys
| Document Number | PRC-017
| Document Revision | 00
Pain Clinical Application and Web Portal Verification
Test Procedure | Expected Results | Pass/Fail | Initials | Date | Notes
GAD7
Click GAD-7 button | Complete GAD-7 page is displayed and Next button (enabled) | Pass | BM | 2025-07-30 15:56
Review text in upper left hand corner next to home icon | Text says "Surveys GAD-7" | Pass | BM | 2025-07-30 15:56
Click on the Help icon | Help text for page is displayed | Pass | BM | 2025-07-30 15:56
Click Close Help icon | Help text for page is closed | Pass | BM | 2025-07-30 15:56
Click on Home icon in top left corner | Confirm Exit screen is displayed | Pass | BM | 2025-07-30 15:56
Click Cancel button | Complete GAD-7 page is displayed and Next button (enabled) | Pass | BM | 2025-07-30 15:56
Click Next button | First question appears of the assessment | Pass | BM | 2025-07-30 15:56
Select the any radio button for first 7 questions and Next button | Questions appear until question 7 is submitted | Pass | BM | 2025-07-30 15:56
Verify the Next button is enabled, then select any radio button and click the Next button | Question 8 is submitted then GAD-7 Complete page displayed with Done button (enabled) | Pass | BM | 2025-07-30 15:56
Click on the Help icon | Help text for page is displayed | Pass | BM | 2025-07-30 15:56
Click Close Help icon | Help text for page is closed | Pass | BM | 2025-07-30 15:56
Click Done button | Baseline Home screen displayed | Pass | BM | 2025-07-30 15:56
Verify home page | Surveys: GAD-7 (checked), PHQ-9 (enabled), PSQI (disabled), BPI (disabled), FIQR (disabled), HFUE (disabled), PGIC (disabled) If HFUE and PGIC are not showing on your screen and you are not on visit day 28 or 196 then this is not a bug. Otherwise please mark as failed. Note the expected results for the home screen are based on the surveys being present. | Pass | BM | 2025-07-30 15:56
PHQ9
Click PHQ-9 button | Complete PHQ-9 page is displayed and Next button (enabled) | Pass | BM | 2025-07-30 15:56
Review text in upper left hand corner next to home icon | Text says "Surveys PHQ-9" | Pass | BM | 2025-07-30 15:56
Click on the Help icon | Help text for page is displayed | Pass | BM | 2025-07-30 15:56
Click Close Help icon | Help text for page is closed | Pass | BM | 2025-07-30 15:56
Click on Home icon in top left corner | Confirm Exit screen is displayed | Pass | BM | 2025-07-30 15:56
Click Cancel button | Complete PHQ-9 page is displayed and Next button (enabled) | Pass | BM | 2025-07-30 15:56
Click Next button | First question appears of the assessment | Pass | BM | 2025-07-30 15:56
Select the any radio button for first 8 questions and Next button | Questions appear until question 8 is submitted | Pass | BM | 2025-07-30 15:56
Select the fourth option for question 9 | Questions 9 is answered | Pass | BM | 2025-07-30 15:56
Verify the Next button is enabled, then select any radio button and click the Next button | Question 10 is submitted then PHQ-9 Complete page displayed with Done button (enabled) | Pass | BM | 2025-07-30 15:56
Click on the Help icon | Help text for page is displayed | Pass | BM | 2025-07-30 15:56
Click Close Help icon | Help text for page is closed | Pass | BM | 2025-07-30 15:56
Click Done button | Baseline Home screen displayed | Pass | BM | 2025-07-30 15:56
Verify home page | Surveys: GAD-7 (checked), PHQ-9 (checked), PSQI (enabled), BPI (disabled), FIQR (disabled), HFUE (disabled), PGIC (disabled) | Pass | BM | 2025-07-30 15:56
PSQI
Click PSQI button | Complete PSQI page is displayed and Next button (enabled) | Pass | BM | 2025-07-30 15:56
Review text in upper left hand corner next to home icon | Text says "Surveys PSQI" | Pass | BM | 2025-07-30 15:56
Click on the Help icon | Help text for page is displayed | Pass | BM | 2025-07-30 15:56
Click Close Help icon | Help text for page is closed | Pass | BM | 2025-07-30 15:56
Click on Home icon in top left corner | Confirm Exit screen is displayed | Pass | BM | 2025-07-30 15:56
Click Cancel button | Complete PSQI page is displayed and Next button (enabled) | Pass | BM | 2025-07-30 15:56
Click Next button | First question appears of the assessment | Pass | BM | 2025-07-30 15:56
Enter data or select the any radio button for all 19 questions and Next button | Questions appear until question 19 is submitted then PSQI Complete page displayed with Done button (enabled) | Pass | BM | 2025-07-30 15:56
Click on the Help icon | Help text for page is displayed | Pass | BM | 2025-07-30 15:56
Click Close Help icon | Help text for page is closed | Pass | BM | 2025-07-30 15:56
Click Done button | Baseline Home screen displayed | Pass | BM | 2025-07-30 15:56
Verify home page | Surveys: GAD-7 (checked), PHQ-9 (checked), PSQI (checked), BPI (enabled), FIQR (disabled), HFUE (disabled), PGIC (disabled) | Pass | BM | 2025-07-30 15:56
BPI
Click BPI button | Complete BPi page is displayed and Next button (enabled) | Pass | BM | 2025-07-30 15:56
Review text in upper left hand corner next to home icon | Text says "Surveys BPI" | Pass | BM | 2025-07-30 15:56
Click on the Help icon | Help text for page is displayed | Pass | BM | 2025-07-30 15:56
Click Close Help icon | Help text for page is closed | Pass | BM | 2025-07-30 15:56
Click on Home icon in top left corner | Confirm Exit screen is displayed | Pass | BM | 2025-07-30 15:56
Click Cancel button | Complete BPI page is displayed and Next button (enabled) | Pass | BM | 2025-07-30 15:56
Click Next button | First question appears of the assessment | Pass | BM | 2025-07-30 15:56
Select any values or radio button for all 13 questions and Next button | Questions appear until question 12 is submitted then BPI Complete page displayed with Done button (enabled) | Pass | BM | 2025-07-30 15:56
Click on the Help icon | Help text for page is displayed | Pass | BM | 2025-07-30 15:56
Click Close Help icon | Help text for page is closed | Pass | BM | 2025-07-30 15:56
Click Done button | Baseline Home screen displayed | Pass | BM | 2025-07-30 15:56
Verify home page | Surveys: GAD-7 (checked), PHQ-9 (checked), PSQI (checked), BPI (checked), FQIR (enabled), HFUE (disabled), PGIC (disabled) | Pass | BM | 2025-07-30 15:56
FIQR
Click FIQR button | Complete FIQR page is displayed and Next button (enabled) | Pass | BM | 2025-07-30 15:56
Review text in upper left hand corner next to home icon | Text says "Surveys FIQR" | Pass | BM | 2025-07-30 15:56
Click on the Help icon | Help text for page is displayed | Pass | BM | 2025-07-30 15:56
Click Close Help icon | Help text for page is closed | Pass | BM | 2025-07-30 15:56
Click on Home icon in top left corner | Confirm Exit screen is displayed | Pass | BM | 2025-07-30 15:56
Click Cancel button | Complete FIQR page is displayed and Next button (enabled) | Pass | BM | 2025-07-30 15:56
Click Next button | First question appears of the assessment | Pass | BM | 2025-07-30 15:56
Select any values or radio button for all 21 questions and Next button | Questions appear until question 21 is submitted then FIQR Complete page displayed with Done button (enabled) | Pass | BM | 2025-07-30 15:56
Click on the Help icon | Help text for page is displayed | Pass | BM | 2025-07-30 15:56
Click Close Help icon | Help text for page is closed | Pass | BM | 2025-07-30 15:56
Click Done button | Baseline Home screen displayed | Pass | BM | 2025-07-30 15:56
Verify home page | Surveys: GAD-7 (checked), PHQ-9 (checked), PSQI (checked), BPI (checked), FQIR (checked), HFUE (enabled), PGIC (disabled) | Pass | BM | 2025-07-30 15:56
HFUE
ONLY TEST DURING DAY 28 AND DAY 196 VISIT
Click HFUE Button | Complete HFUE page is displayed and Next button (enabled) | Pass | BM | 2025-07-30 15:56
Review text in upper left hand corner next to home icon | Text says "Surveys HFUE" | Pass | BM | 2025-07-30 15:56
Click on the Help icon | Help text for page is displayed | Pass | BM | 2025-07-30 15:56
Click Close Help icon | Help text for page is closed | Pass | BM | 2025-07-30 15:56
Click on Home icon in top left corner | Confirm Exit screen is displayed | Pass | BM | 2025-07-30 15:56
Click Cancel button | Complete HFUE page is displayed and Next button (enabled) | Pass | BM | 2025-07-30 15:56
Click Next button | First question appears of the assessment | Pass | BM | 2025-07-30 15:56
Select the value 5 for each of the first 6 questions. Press Next on each screen to prodeed. | Option 5 selected, then Next button enabled on each screen, no textarea inputs shown. | Pass | BM | 2025-07-30 15:56
Press the previous button until you are back on question 1 | Confirm previous entries are all still selected. | Pass | BM | 2025-07-30 15:56
Select the value 4 for each of the first 6 questions, enter 'test' into the textarea on each one. Press Next on each screen to prodeed. | Option 4 selected, then Next button enabled on each screen, textarea inputs accept 'test' copy. | Pass | BM | 2025-07-30 15:56
Press the previous button until you are back on question 1 | Option 4 selected, textarea inputs accept 'test' copy. | Pass | BM | 2025-07-30 15:56
Select Next for questions 1-6 | Next button opens next question, you are on question 7 | Pass | BM | 2025-07-30 15:56
Select No on dropdown menu | Next button enabled | Pass | BM | 2025-07-30 15:56
Select Yes on dropdown menu | Textarea and two radio button questions are displayed. Next button disabled | Pass | BM | 2025-07-30 15:56
Select any option for 'Did these experiences make you less keen to use the device' | Option selected, Next button still disabled | Pass | BM | 2025-07-30 15:56
Select any option for 'Did these experiences change over the course of the study' | Option selected, Next button still disabled | Pass | BM | 2025-07-30 15:56
Enter 'test' into the textarea | Copy shows up in text area and Next button enabled | Pass | BM | 2025-07-30 15:56
Click Next button | Question 8 shows up | Pass | BM | 2025-07-30 15:56
Click previous button | Question 7 results appear | Pass | BM | 2025-07-30 15:56
Click Next button | Question 8 shows up | Pass | BM | 2025-07-30 15:56
Type 'word1' into first textinput | Next button disabled | Pass | BM | 2025-07-30 15:56
Type 'word2' into first textinput | Next button disabled | Pass | BM | 2025-07-30 15:56
Type 'word3' into first textinput | Next button enabled | Pass | BM | 2025-07-30 15:56
Click Next button | Question 9 shows up | Pass | BM | 2025-07-30 15:56
Click previous button | Question 8 results appear | Pass | BM | 2025-07-30 15:56
Click Next button | Question 9 shows up | Pass | BM | 2025-07-30 15:56
Select 'Stayed about the same' from dropdown | Next button enabled | Pass | BM | 2025-07-30 15:56
Click Next button | Question 10 shows up if on Day196 visit, otherwise HFUE form complete shows up so skip Question 10 test | Pass | BM | 2025-07-30 15:56
Click previous button | Question 9 results appear | Pass | BM | 2025-07-30 15:56
Click Next button | Question 10 shows up | Pass | BM | 2025-07-30 15:56
Select 'Stayed about the same' from dropdown | Next button enabled | Pass | BM | 2025-07-30 15:56
Click Next button | HFUE Form complete shows up | Pass | BM | 2025-07-30 15:56
Click Done button | Baseline Home screen displayed | Pass | BM | 2025-07-30 15:56
Verify home page | Surveys: GAD-7 (checked), PHQ-9 (checked), PSQI (checked), BPI (checked), FQIR (checked), HFUE (checked), PGIC (enabled) | Pass | BM | 2025-07-30 15:56
PGIC
ONLY TEST DURING DAY 28 AND DAY 196 VISIT
Click PGIC Button | Complete PGIC page is displayed and Next button (enabled) | Pass | BM | 2025-07-30 15:56
Review text in upper left hand corner next to home icon | Text says "Surveys PGIC" | Pass | BM | 2025-07-30 15:56
Click on the Help icon | Help text for page is displayed | Pass | BM | 2025-07-30 15:56
Click Close Help icon | Help text for page is closed | Pass | BM | 2025-07-30 15:56
Click on Home icon in top left corner | Confirm Exit screen is displayed | Pass | BM | 2025-07-30 15:56
Click Cancel button | Complete PGIC page is displayed and Next button (enabled) | Pass | BM | 2025-07-30 15:56
Click Next button | First question appears of the assessment | Pass | BM | 2025-07-30 15:56
Select any values or radio button for all 2 questions and Next button | Questions appear until question 2 is submitted then PGIC Complete page displayed with Done button (enabled) | Pass | BM | 2025-07-30 15:56
Click Done button | Baseline Home screen displayed | Pass | BM | 2025-07-30 15:56
Verify home page | Surveys: GAD-7 (checked), PHQ-9 (checked), PSQI (checked), BPI (checked), FQIR (checked), HFUE (checked), PGIC (checked) | Pass | BM | 2025-07-30 15:56
Formulas:
Date = IF([Initials]<>"",Now(),"")

## Web and Tablet Day 14
| Document Number | PRC-017
| Document Revision | 00
Pain Clinical Application and Web Portal Verification
Test Procedure | Expected Results | Pass/Fail | Initials | Date | Notes
Day 14 Visit on Web Portal
Login | Home screen displayed | Pass | BM | 2025-07-30 15:56
On home screen, find patient, click kebab menu and click day 14 visit | Patient adherence screen displayed | Pass
Confirm patient adherence screen shows, we do not care about content as this is tested elsewhere | Patient adherence screen displayed | Pass | BM | 2025-07-30 15:56
Scroll to bottom of screen, Eligibility Criteria Review is visible and there is a check box | Eligibility Criteria Review is visible | Pass | BM | 2025-07-30 15:56
Click Continue button | Patient Profile screen displayed | Pass
Enter 3333333333 into patient phone number field | Form shows Patient Phone Number | Pass | BM | 2025-07-30 15:56
Click Continue button | Medical History form displayed | Pass | BM | 2025-07-30 15:56
Click Previous button | Patient Profile screen displayed with updated phone number | Pass | BM | 2025-07-30 15:56
Click Continue button | Medical History form displayed | Pass | BM | 2025-07-30 15:56
Medical History
Update "Day 1 visit test" to "Day 14 Visit Test" into Patient Medical History field | Form shows Day 14 Test | Pass | BM | 2025-07-30 15:56
Click Continue button | Medications form displayed | Pass | BM | 2025-07-30 15:56
Medications
Click New Medication button | Add Medication modal displayed | Pass | BM | 2025-07-30 15:56
Click Continue button | Verify Patient Data Page Displayed | Pass | BM | 2025-07-30 15:56
Verify Patient Data
Click Review Profile button | Patient Data displayed | Pass | BM | 2025-07-30 15:56
Select data acknowledgement | Check box selected and Continue button appears | Pass | BM | 2025-07-30 15:56
Click Continue button | Electronically Sign Records modal displayed | Pass
Electronically Sign Records
Verify Name = "Jane Doe" or current user name | Name = "Jane Doe" or current user name | Pass | BM | 2025-07-30 15:56
Verify Meaning = "Patient medical data from visit Day 14 Visit" | Meaning = Patient medical data from visit Day 14 Visit" | Pass | BM | 2025-07-30 15:56
Enter Password in field | Field shows asterisk for entry | Pass | BM | 2025-07-30 15:56
Click Electronically Sign button | Day 14 complete page displayed | Pass | BM | 2025-07-30 15:56
Day 14 Visit in the web portal complete
Formulas:
Date = IF([Initials]<>"",Now(),"")

## Web and Tablet Day 28
| Document Number | PRC-017
| Document Revision | 00
Pain Clinical Application and Web Portal Verification
Test Procedure | Expected Results | Pass/Fail | Initials | Date | Notes
Day 28 Visit on Web Portal
Login | Home screen displayed | Pass | BM | 2025-07-30 15:56
On home screen, find patient, click kebab menu and select Day 28 Visit | Patient Adherence screen displayed | Pass | BM | 2025-07-30 15:56
Confirm patient adherence screen shows, we do not care about content as this is tested elsewhere | Patient adherence screen displayed | Pass | BM | 2025-07-30 15:56
Scroll to bottom of screen, select the acknowledgment check box for the Patient Data Check | Check box selected | Pass | BM | 2025-07-30 15:56
Click Continue button | Patient Profile screen displayed | Pass | BM | 2025-07-30 15:56
Enter 4444444444 in patient phone number field | Form shows Patient Phone Number | Pass | BM | 2025-07-30 15:56
Click Continue button | Medical History form displayed | Pass | BM | 2025-07-30 15:56
Click Previous button | Patient Profile screen displayed with updated phone number | Pass | BM | 2025-07-30 15:56
Click Continue button | Medical History form displayed | Pass | BM | 2025-07-30 15:56
Medical History
Update "Day 14 visit Test" to "Day 28 Visit Test" into Patient Medical History field | Form shows Patient Medical History | Pass | BM | 2025-07-30 15:56
Click Continue button | Medications form displayed | Pass | BM | 2025-07-30 15:56
Medications
On Aleve, click kebab menu and select Archive | Are you sure you want to archive this medication model displayed | Pass | BM | 2025-07-30 15:56
Click Archive button | X displayed next to Aleve | Pass | BM | 2025-07-30 15:56
Click Continue button | Verify Patient Data Page Displayed | Pass | BM | 2025-07-30 15:56
Verify Patient Data
Click Review Profile button | Patient Data displayed | Pass | BM | 2025-07-30 15:56
Select data acknowledgement | Check box selected and Continue button appears | Pass | BM | 2025-07-30 15:56
Click Continue button | Electronically Sign Records modal displayed | Pass | BM | 2025-07-30 15:56
Electronically Sign Records
Verify Name = "Jane Doe" or current user name | Name = "Jane Doe" or current user name | Pass | BM | 2025-07-30 15:56
Verify Meaning = "Patient medical data from visit Day 28 Visit" | Meaning = Patient medical data from visit Day 28 Visit" | Pass | BM | 2025-07-30 15:56
Enter Password in field | Field shows asterisk for entry | Pass | BM | 2025-07-30 15:56
Click Electronically Sign button | Screen asking if user wants to continue onto phase 2 shows. | Pass | BM | 2025-07-30 15:56
Click Accept button | Screen updates showing user does not require a new mask, but tells coordinator to ask patient to proceed onto phase 2. | Pass | BM | 2025-07-30 15:56
Day 28 Visit on Tablet
Open App | Home screen displayed | Pass | BM | 2025-07-30 15:56
Click on the Settings button | Setting page is displayed. Sync data button (enabled). Register Mask button (disabled), Sync Mask Logs (enabled) | Pass | BM | 2025-07-30 15:56
Click Sync Data button | Setting page is displayed. Sync data button (enabled). Register Mask button (disabled), Sync Mask Logs (enabled) | Pass | BM | 2025-07-30 15:56
Click Home button | Home screen displayed | Pass | BM | 2025-07-30 15:56
Complete New Surveys Tab to ensure HFUE and PGIC surveys show up properly. | Surveys complete | Pass | BM | 2025-07-30 15:56
Day 28 Visit in the web portal complete
Formulas:
Date = IF([Initials]<>"",Now(),"")

## Web Day 56 Visit
| Document Number | PRC-017
| Document Revision | 00
Pain Clinical Application and Web Portal Verification
Test Procedure | Expected Results | Pass/Fail | Initials | Date | Notes
Day 56 Visit on Web Portal
Login | Home screen displayed | Pass | BM | 2025-07-30 15:56
On home screen, find patient, click kebab menu and click day 56 visit | Patient adherence screen displayed | Pass
Confirm patient adherence screen shows, we do not care about content as this is tested elsewhere | Patient adherence screen displayed | Pass | BM | 2025-07-30 15:56
Scroll to bottom of screen, Eligibility Criteria Review is visible and there is a check box | Eligibility Criteria Review is visible | Pass | BM | 2025-07-30 15:56
Click Continue button | Patient Profile screen displayed | Pass
Enter 3333333333 into patient phone number field | Form shows Patient Phone Number | Pass | BM | 2025-07-30 15:56
Click Continue button | Medical History form displayed | Pass | BM | 2025-07-30 15:56
Click Previous button | Patient Profile screen displayed with updated phone number | Pass | BM | 2025-07-30 15:56
Click Continue button | Medical History form displayed | Pass | BM | 2025-07-30 15:56
Medical History
Update "Day 28 visit test" to "Day 56 Visit Test" into Patient Medical History field | Form shows Day 56 Test | Pass | BM | 2025-07-30 15:56
Click Continue button | Medications form displayed | Pass | BM | 2025-07-30 15:56
Medications
Click New Medication button | Add Medication modal displayed | Pass | BM | 2025-07-30 15:56
Click Continue button | Verify Patient Data Page Displayed | Pass | BM | 2025-07-30 15:56
Verify Patient Data
Click Review Profile button | Patient Data displayed | Pass | BM | 2025-07-30 15:56
Select data acknowledgement | Check box selected and Continue button appears | Pass | BM | 2025-07-30 15:56
Click Continue button | Electronically Sign Records modal displayed | Pass
Electronically Sign Records
Verify Name = "Jane Doe" or current user name | Name = "Jane Doe" or current user name | Pass | BM | 2025-07-30 15:56
Verify Meaning = "Patient medical data from visit Day 56 Visit" | Meaning = Patient medical data from visit Day 56 Visit" | Pass | BM | 2025-07-30 15:56
Enter Password in field | Field shows asterisk for entry | Pass | BM | 2025-07-30 15:56
Click Electronically Sign button | Day 56 complete page displayed | Pass | BM | 2025-07-30 15:56
Day 56 Visit in the web portal complete
Formulas:
Date = IF([Initials]<>"",Now(),"")

## Web Day 112 Visit
| Document Number | PRC-017
| Document Revision | 00
Pain Clinical Application and Web Portal Verification
Test Procedure | Expected Results | Pass/Fail | Initials | Date | Notes
Day 112 Visit on Web Portal
Login | Home screen displayed | Pass | BM | 2025-07-30 15:56
On home screen, find patient, click kebab menu and click day 112 visit | Patient adherence screen displayed | Pass
Confirm patient adherence screen shows, we do not care about content as this is tested elsewhere | Patient adherence screen displayed | Pass | BM | 2025-07-30 15:56
Scroll to bottom of screen, Eligibility Criteria Review is visible and there is a check box | Eligibility Criteria Review is visible | Pass | BM | 2025-07-30 15:56
Click Continue button | Patient Profile screen displayed | Pass
Enter 3333333333 into patient phone number field | Form shows Patient Phone Number | Pass | BM | 2025-07-30 15:56
Click Continue button | Medical History form displayed | Pass | BM | 2025-07-30 15:56
Click Previous button | Patient Profile screen displayed with updated phone number | Pass | BM | 2025-07-30 15:56
Click Continue button | Medical History form displayed | Pass | BM | 2025-07-30 15:56
Medical History
Update "Day 56 visit test" to "Day 112 Visit Test" into Patient Medical History field | Form shows Day 112 Test | Pass | BM | 2025-07-30 15:56
Click Continue button | Medications form displayed | Pass | BM | 2025-07-30 15:56
Medications
Click New Medication button | Add Medication modal displayed | Pass | BM | 2025-07-30 15:56
Click Continue button | Verify Patient Data Page Displayed | Pass | BM | 2025-07-30 15:56
Verify Patient Data
Click Review Profile button | Patient Data displayed | Pass | BM | 2025-07-30 15:56
Select data acknowledgement | Check box selected and Continue button appears | Pass | BM | 2025-07-30 15:56
Click Continue button | Electronically Sign Records modal displayed | Pass
Electronically Sign Records
Verify Name = "Jane Doe" or current user name | Name = "Jane Doe" or current user name | Pass | BM | 2025-07-30 15:56
Verify Meaning = "Patient medical data from visit Day 112 Visit" | Meaning = Patient medical data from visit Day 112 Visit" | Pass | BM | 2025-07-30 15:56
Enter Password in field | Field shows asterisk for entry | Pass | BM | 2025-07-30 15:56
Click Electronically Sign button | Day 112 complete page displayed | Pass | BM | 2025-07-30 15:56
Day 112 Visit in the web portal complete
Formulas:
Date = IF([Initials]<>"",Now(),"")

## Android Phase 2 at Home
| Document Number | PRC-017
| Document Revision | 00
Pain Clinical Application and Web Portal Verification
Test Procedure | Expected Results | Pass/Fail | Initials | Date | Notes
Android Phase 2 at home, set tablet to 6am the following day
Ensure morning logs capture pain,sleep fields | Morning log appears and captures those data. | Pass | BM | 2025-07-30 15:56
Ensure regular sessions available throughout the day | Regular therapy sessions available | Pass
Android Phase 2 at home, set tablet to 6pm that same day
Ensure evening logs capture pain, medical systems usage, sleep [optional], meds fields. | Evening log appears and captures those data. | Pass | BM | 2025-07-30 15:56
Ensure patient is not asked to enter Aleve during daily log. | Aleve is not asked during medication entry. | Pass | BM | 2025-07-30 15:56
Ensure end of day sessions available at night | End of day therapy sessions available | Pass | BM | 2025-07-30 15:56
Survey Reminders and Surveys
On tablet to 22 days from now
Load home screen | Suvery remiders appear | Pass | BM | 2025-07-30 15:56
On tablet to 24 days from now
Load home screen | Surveys active | Pass | BM | 2025-07-30 15:56
On tablet to 78 days from now
Load home screen | Suvery remiders appear | Pass | BM | 2025-07-30 15:56
On tablet to 80 days from now
Load home screen | Surveys active | Pass | BM | 2025-07-30 15:56
On tablet to 162 days from now
Load home screen | Suvery remiders appear | Pass | BM | 2025-07-30 15:56
On tablet to 164 days from now
Load home screen | Surveys active, and HFUE and PGIC surveys appear | Pass | BM | 2025-07-30 15:56
Formulas:
Date = IF([Initials]<>"",Now(),"")

## Web and Tablet Day 196
| Document Number | PRC-017
| Document Revision | 00
Pain Clinical Application and Web Portal Verification
Test Procedure | Expected Results | Pass/Fail | Initials | Date | Notes
Day 196 Visit on Web Portal
Set tablet time to current time
Login | Home screen displayed | Pass | BM | 2025-07-30 15:56
On home screen, find patient, click kebab menu and select Day 196 Visit | Patient Adherence screen displayed | Pass | BM | 2025-07-30 15:56
Scroll to bottom of screen, select the acknowledgment check box for the Patient Data Check | Check box selected | Pass | BM | 2025-07-30 15:56
Click Continue button | Patient Profile screen displayed | Pass | BM | 2025-07-30 15:56
Enter 4444444444 in patient phone number field | Form shows Patient Phone Number | Pass | BM | 2025-07-30 15:56
Click Continue button | Medical History form displayed | Pass | BM | 2025-07-30 15:56
Click Previous button | Patient Profile screen displayed with updated phone number | Pass | BM | 2025-07-30 15:56
Click Continue button | Medical History form displayed | Pass | BM | 2025-07-30 15:56
Medical History
Update "Day 28 visit Test" to "Day 196 Visit Test" into Patient Medical History field | Form shows Patient Medical History | Pass | BM | 2025-07-30 15:56
Click Continue button | Medications form displayed | Pass | BM | 2025-07-30 15:56
Medications
On Aleve, click kebab menu and select Archive | Are you sure you want to archive this medication model displayed | Pass | BM | 2025-07-30 15:56
Click Archive button | X displayed next to Aleve | Pass | BM | 2025-07-30 15:56
Click Continue button | Verify Patient Data Page Displayed | Pass | BM | 2025-07-30 15:56
Verify Patient Data
Click Review Profile button | Patient Data displayed | Pass | BM | 2025-07-30 15:56
Select data acknowledgement | Check box selected and Continue button appears | Pass | BM | 2025-07-30 15:56
Click Continue button | Electronically Sign Records modal displayed | Pass | BM | 2025-07-30 15:56
Electronically Sign Records
Verify Name = "Jane Doe" or current user name | Name = "Jane Doe" or current user name | Pass | BM | 2025-07-30 15:56
Verify Meaning = "Patient medical data from visit Day 196 Visit" | Meaning = Patient medical data from visit Day 196 Visit" | Pass | BM | 2025-07-30 15:56
Enter Password in field | Field shows asterisk for entry | Pass | BM | 2025-07-30 15:56
Click Electronically Sign button | Electronically Sign modal displayed | Pass | BM | 2025-07-30 15:56
Electronically Sign Records
Verify Name = "Jane Doe" or current user name | Name = "Jane Doe" or current user name | Pass | BM | 2025-07-30 15:56
Verify Meaning = "Patient medical data from visit Day 196 Visit" | Meaning = Patient medical data from visit Day 196 Visit" | Pass | BM | 2025-07-30 15:56
Enter Password in field | Field shows asterisk for entry | Pass | BM | 2025-07-30 15:56
Click Electronically Sign button | Initiate Follow Up Stage screen displayed | Pass | BM | 2025-07-30 15:56
Day 196 Visit on Tablet.
Open App | Home screen displayed | Pass | BM | 2025-07-30 15:56
Click on the Settings button | Setting page is displayed. Sync data button (enabled). Register Mask button (disabled), Sync Mask Logs (enabled) | Pass | BM | 2025-07-30 15:56
Click Sync Data button | Setting page is displayed. Sync data button (enabled). Register Mask button (disabled), Sync Mask Logs (hidden) | Pass | BM | 2025-07-30 15:56
Click Home button | Home screen displayed. Morning Log, Evening log, Regular session and End of day session are hidden | Pass | BM | 2025-07-30 15:56
Complete Day 196 visit on web portal
Formulas:
Date = IF([Initials]<>"",Now(),"")

## Android Medical System Usage an
| Document Number | PRC-017
| Document Revision | 00
Pain Clinical Application and Web Portal Verification
Test Procedure | Expected Results | Pass/Fail | Initials | Date | Notes
Medical System Usage test to 6pm today
Complete evening log up until Did you see your doctor today screen | Screens complete | Pass | BM
Click The Yes "did you see a doctor today?" | Next button. enabled | Pass | BM | 2025-07-30 15:56
Click on the Help icon | Help text for page is displayed | Pass | BM | 2025-07-30 15:56
Click Close Help icon | Help text for page is closed | Pass | BM | 2025-07-30 15:56
Click the Next button | Type of doctor screen shown. | Pass | BM | 2025-07-30 15:56
Click on the Help icon | Help text for page is displayed | Pass | BM | 2025-07-30 15:56
Click Close Help icon | Help text for page is closed | Pass | BM | 2025-07-30 15:56
Select Other | Next button disabled Other selected | Pass
Type 'test' in the text area box | Next button enabled Other Selected Textarea has 'test' | Pass
Deselect other | Next button disabled Other not selected Textarea keeps copy | Pass
Select Primary Care physician | Next button enabled Primary Care Physician selected | Pass | BM | 2025-07-30 15:56
Select OB/GYN | Next button enabled Primary Care Physician selected OB/GYN Selected | Pass
Select Primary Care physician | Next button enabled Primary Care Physician not selected OB/GYN Selected | Pass
Click the Next button | Visits emergency or unplanned screen shown | Pass | BM | 2025-07-30 15:56
Click on the Help icon | Help text for page is displayed | Pass | BM | 2025-07-30 15:56
Click Close Help icon | Help text for page is closed | Pass | BM | 2025-07-30 15:56
Click Previous button | Previous screen loads w/ data | Pass
Click the Next button | Visits emergency or unplanned screen shown | Pass | BM | 2025-07-30 15:56
Select Yes | Next button enabled | Pass | BM | 2025-07-30 15:56
Click Next button | How long were you there sceen shown | Pass | BM | 2025-07-30 15:56
Click on the Help icon | Help text for page is displayed | Pass | BM | 2025-07-30 15:56
Click Close Help icon | Help text for page is closed | Pass | BM | 2025-07-30 15:56
Enter 49 into the. text area | Next button enabled | Pass | BM | 2025-07-30 15:56
Click Next button | Error message shows on screen that hours cannot exceed 24. | Pass
Enter 4 into the. text area | Next button enabled | Pass
Click Next button | Why did you go screen shown | Pass | BM | 2025-07-30 15:56
Click Previous button | Previous screen loads w/ data | Pass
Click the Next button | Why did you go screen shown | Pass
Click on the Help icon | Help text for page is displayed | Pass | BM | 2025-07-30 15:56
Click Close Help icon | Help text for page is closed | Pass | BM | 2025-07-30 15:56
Select Check up / follow up from prior appointment | Next button enabled | Pass | BM | 2025-07-30 15:56
Click the Next button. | Any new medications screen shown | Pass | BM | 2025-07-30 15:56
Click Previous button | Previous screen loads w/ data | Pass
Click the Next button | Any new medications screen shown | Pass
Click on the Help icon | Help text for page is displayed | Pass | BM | 2025-07-30 15:56
Click Close Help icon | Help text for page is closed | Pass | BM | 2025-07-30 15:56
Select Yes | Next button enabled | Pass | BM | 2025-07-30 15:56
Click next button | Medication change shows up | Pass
Click the Next button | How to screen shown | Pass | BM | 2025-07-30 15:56
Click on the Help icon | Help text for page is displayed | Pass | BM | 2025-07-30 15:56
Click Close Help icon | Help text for page is closed | Pass | BM | 2025-07-30 15:56
Click the Next button | New medication screen shown | Pass | BM | 2025-07-30 15:56
Click on the Help icon | Help text for page is displayed | Pass | BM | 2025-07-30 15:56
Click Close Help icon | Help text for page is closed | Pass | BM | 2025-07-30 15:56
Enter the following into the form: Active: oxycontin, mgPerDay: 20, Doses Per Day: 2, Regularly Scheduled, and. Capsule | Next button enabled | Pass | BM | 2025-07-30 15:56
Click Next button | Another medication to add screen shown. | Pass | BM | 2025-07-30 15:56
Select Yes | New medication screen shown | Pass | BM | 2025-07-30 15:56
Enter the following into the form: Active: IBUPROFEN, mgPerDay: 20, Doses Per Day: 2, As Needed, and. Capsule | Next button enabled | Pass | BM | 2025-07-30 15:56
Click Next button | Another medication to add screen shown. | Pass | BM | 2025-07-30 15:56
Select No | Daily regularly scheduled medications log shown with an option to fill in data for oxycontin | Pass | BM | 2025-07-30 15:56
Enter a value for each medications and click next | Daily as needed medications log shown with an option to fill in data for IBUPROFEN | Pass | BM | 2025-07-30 15:56
Click next on anything else to add screen | Evening log complete screen shows | Pass | BM | 2025-07-30 15:56
Click done | Patient goes back to Home screen | Pass | BM | 2025-07-30 15:56
Check Patient Medication Upate Alert on Web Portal
On home screen, find your patient record, then click kebab menu and select Patient Record | Patient Adherence screen displayed | Pass | BM | 2025-07-30 15:56
Click on Medications side tab | Medications tab shows and alerts coordinator to change in medications. Medication table below shows the user is now taking oxycontin and IBUPROFEN | Pass | BM | 2025-07-30 15:56
Click save | Modal opens asking for reason and password | Pass | BM | 2025-07-30 15:56
Fill in fields on modal and click Save Changes | Modal closes and you see history of medications | Pass | BM | 2025-07-30 15:56
Medical System Usage test to 6pm tomorrow
Complete evening log anyway you want. But confirm the oxycontin and ibuprofen medications appear in the medication log. | You are forced to log medications for oxycontin and alleve. | Pass | BM | 2025-07-30 15:56
Formulas:
Date = IF([Initials]<>"",Now(),"")

## Web Patient Record Data Updates
| Document Number | PRC-017
| Document Revision | 00
Pain Clinical Application and Web Portal Verification
Test Procedure | Expected Results | Pass/Fail | Initials | Date | Notes
Patient Record Data Updates on Web Portal
On home screen, find completed patient, click kebab menu and select Patient Record | Patient Adherence screen displayed | Pass | BM | 2025-07-30 15:56
Click on Medical History side navigation | Medical History versions screen displayed. There should be four entrees unless the history was edited outside of an in person visit. | Pass | BM | 2025-07-30 15:56
Click kebab menu on the Day 1 Visit and select view | Medical History modal opens as read only | Pass | BM | 2025-07-30 15:56
Click Close button | Modal closes | Pass | BM | 2025-07-30 15:56
Click Update Medical History button | Medical History modal opens showing current version with ability to edit fields | Pass | BM | 2025-07-30 15:56
Click Save Changes button | Form updates to show you must provide a reason for making the change | Pass | BM | 2025-07-30 15:56
Delete the values in the Patient Medical History fields | Form updates to show required fields error message | Pass | BM | 2025-07-30 15:56
Click Cancel | Modal closes | Pass | BM | 2025-07-30 15:56
Click Update Medical History button | Modal opens showing current version with ability to edit fields | Pass | BM | 2025-07-30 15:56
Change Patient Medical History field to "Patient Record Data Update Test" | Form shows updated Patient Medical History | Pass | BM | 2025-07-30 15:56
Enter password and "Patient Record Data Update Test" into Change reason text area | Form shows Change Reason | Pass | BM | 2025-07-30 15:56
Click Save Changes button | Medical History versions screen displayed and a new version appears in table | Pass
Click kebab menu on the first row and select view | Medical History modal opens as read only | Pass | BM | 2025-07-30 15:56
Click Close button | Modal closes | Pass | BM | 2025-07-30 15:56
Click Patient Profile side navigation | Patient Profile versions screen displayed | Pass | BM | 2025-07-30 15:56
Click the kebab menu in the first row and select View | Patient Profile modal opens as read only | Pass | BM | 2025-07-30 15:56
Click Close button | Modal closes | Pass | BM | 2025-07-30 15:56
Click Update Patient Profile button | Patient Profile modal opens showing editable elements for Patient Phone Number, Gender, Race and Change Reason | Pass | BM | 2025-07-30 15:56
Click Save Changes button | Form updates to show you must provide a reason for making the change | Pass | BM | 2025-07-30 15:56
Delete the phone number | Form shows Phone number cannot be left blank | Pass | BM | 2025-07-30 15:56
Enter "111" in the phone number field | Form shows Phone number must be 10 digits | Pass | BM | 2025-07-30 15:56
Enter "123456789" | Form shows Phone number must be 10 digits | Pass | BM | 2025-07-30 15:56
Click Cancel | Modal closes | Pass | BM | 2025-07-30 15:56
Click Update Patient Profile button | Patient Profile modal opens showing editable elements for Patient Phone Number, Gender, Race and Change Reason | Pass | BM | 2025-07-30 15:56
Enter "3333333333" in the phone number field | Field updates | Pass | BM | 2025-07-30 15:56
Select "Male" for Gender from dropdown menu | Field updates | Pass | BM | 2025-07-30 15:56
Enter Password, "Patient Profile Update Test" into Change reason text area | Field updates | Pass | BM | 2025-07-30 15:56
Click Save Changes button | Modal closes and new version appears in table | Pass | BM | 2025-07-30 15:56
Click the kebab menu in the first row and select View | Patient Profile modal opens as read only | Pass | BM | 2025-07-30 15:56
Formulas:
Date = IF([Initials]<>"",Now(),"")

## Web Call,Lock,Exclude,wPIrole
| Document Number | PRC-017
| Document Revision | 00
Pain Clinical Application and Web Portal Verification
Test Procedure | Expected Results | Pass/Fail | Initials | Date | Notes
Patient Exclude / Unexclude on Web Portal
Log into portal with the following user: coordinator@sana.io sana12345 | Home screen displayed | Pass | BM | 2025-07-30 15:56
On home screen, find patient (status = complete), click kebab menu and select Patient Record | Patient Adherence screen displayed with status: "Complete" and Exclude button in top right corner | Pass | BM | 2025-07-30 15:56
Confirm the Lock Patient Data button is not shown | Button is not visible | Pass | BM | 2025-07-30 15:56
Click Exclude button in top right corner | Exclude Patient modal opens | Pass | BM | 2025-07-30 15:56
Click Cancel | Modal closes | Pass | BM | 2025-07-30 15:56
Click Exclude button in top right corner | Exclude Patient modal opens | Pass | BM | 2025-07-30 15:56
Click the exclude button to show form error messages | Form shows Reason and Description fields are required error messages | Pass | BM | 2025-07-30 15:56
Select "Patient withdrew consent" from dropdown menu, Enter "Exclude Patient Test" in the Description field and Enter Password | Form shows updated fields | Pass | BM | 2025-07-30 15:56
Click Exclude button | Patient Adherence screen displayed with status: "Excluded" and Unexclude button in top right corner | Pass | BM | 2025-07-30 15:56
Click Home button | Home screen displayed and patient status shows EXCLUDED (patient should be in first row, but possible they are not) | Pass | BM | 2025-07-30 15:56
For same patient (status = EXCLUDED), click kebab menu and select Patient Record | Patient Adherence screen displayed with status: "Excluded" | Pass | BM | 2025-07-30 15:56
Click Unexclude button in top right corner | Unexclude Patient modal opens | Pass | BM | 2025-07-30 15:56
Click Cancel | Modal closes | Pass | BM | 2025-07-30 15:56
Click Unexclude button in top right corner | Unexclude Patient modal opens | Pass | BM | 2025-07-30 15:56
Click the Unexclude button | Form shows Valid description required error message | Pass | BM | 2025-07-30 15:56
Enter "Unexclude Patient Test" in the Description field and password | Form shows updated field | Pass | BM | 2025-07-30 15:56
Click Unexclude button | Patient Adherence screen displayed with status: "Complete" and Exclude button in top right corner | Pass | BM | 2025-07-30 15:56
Click Patient Profile side navigation | Patient Profile versions screen displayed | Pass | BM | 2025-07-30 15:56
For Patient Excluded Reason, click the kebab menu in the first row and select View | Patient Profile modal opens as read only and the reason and description provided is displayed | Pass | BM | 2025-07-30 15:56
Click Close button | Modal closes | Pass | BM | 2025-07-30 15:56
For Patient Unexcluded Reason, click the kebab menu in the first row and select View | Patient Profile modal opens as read only and the reason and description provided is displayed | Pass | BM | 2025-07-30 15:56
Click Close button | Modal closes | Pass | BM | 2025-07-30 15:56
Patient Call Logs
Click Patient Call Logs side navigation | Patient Calls screen displayed | Pass | BM | 2025-07-30 15:56
Click New Call button | Log New Call modal opens | Pass | BM | 2025-07-30 15:56
Click Log Call button | Form shows Reason and Call details fields are required error messages | Pass | BM | 2025-07-30 15:56
Select "Other" from dropdown menu | Form shows updated field | Pass | BM | 2025-07-30 15:56
Enter "Log New Call Test" in the Call details field | Text entered is displayed | Pass | BM | 2025-07-30 15:56
Enter Password | Asterisks displayed | Pass | BM | 2025-07-30 15:56
Click Log Call button | Modal closes and table updates to show new call | Pass | BM | 2025-07-30 15:56
Click the kebab menu for new call and select Edit Current Version | Edit Call modal displayed with Patient Phone Number (disabled), Date (enabled), Reason = Other (enabled) and Call Details (enabled) | Pass | BM | 2025-07-30 15:56
Update Reason to "Adherence follow up" from dropdown menu | Field populates | Pass | BM | 2025-07-30 15:56
Enter "Edit Log New Call Test" in the Call details field | Text entered is displayed | Pass | BM | 2025-07-30 15:56
Enter Password | Asterisks displayed | Pass | BM | 2025-07-30 15:56
Enter "Edit Log New Call Test" in the Change Reason field | Text entered is displayed | Pass | BM | 2025-07-30 15:56
Click Save Changes button | Modal closes and table updates to show updates | Pass | BM | 2025-07-30 15:56
Click the kebab menu for updated call and select View Version History | Patient Calls version history appears | Pass | BM | 2025-07-30 15:56
On the first row, click the kebab menu and select View | Patient Call modal opens | Pass | BM | 2025-07-30 15:56
Click Close button | modal closes | Pass | BM | 2025-07-30 15:56
Patient Adverse Event Reporting
Click Adverse Events side navigation | Adverse Events screen displayed | Pass | BM | 2025-07-30 15:56
Click New Event button | Log Adverse Event modal opens | Pass | BM | 2025-07-30 15:56
Scroll to the bottom and click Log Event button | Error in form message appears | Pass | BM | 2025-07-30 15:56
Confirm you cannot see the section titled "PI/Medical Monitor Reviewed" | PI/Medical Monitor Reviewed section not present | Pass | BM | 2025-07-30 15:56
Enter "Nausea and Vomiting" in Event Term field | Form shows updated field | Pass | BM | 2025-07-30 15:56
Select "Mild" from Severity dropdown menu | Form shows selected value | Pass | BM | 2025-07-30 15:56
Select "None" from Study Impact dropdown menu | Form shows selected value | Pass | BM | 2025-07-30 15:56
Enter "Patient threw up after their regular session. They also ate a meatball sub right before." in Event Description field | Form shows updated field | Pass | BM | 2025-07-30 15:56
Select "None" from Action Taken dropdown menu | Form shows selected value | Pass | BM | 2025-07-30 15:56
Select "The Patient was prescribed a medication due to this event" | Check box selected and green toastr thrown reminding coordinator to enter medication. | Pass | BM | 2025-07-30 15:56
Select "Yes" from IRB Notified dropdown menu | Form shows selected value and IRB Notification Date field appears next to it | Pass | BM | 2025-07-30 15:56
Select "None" from AE's of Special Interest dropdown menu | Form shows selected value | Pass | BM | 2025-07-30 15:56
Select "Recovering / Resolving" from Outcome dropdown menu | Form shows selected value | Pass | BM | 2025-07-30 15:56
Enter "Patient is feeling better and will run another session tomorrow" in Outcome Notes field | Form shows updated field | Pass | BM | 2025-07-30 15:56
Enter Password | Asterisks displayed | Pass | BM | 2025-07-30 15:56
Click Log Event button | Modal closes, table updates to show adverse event | Pass | BM | 2025-07-30 15:56
Click the kebab menu and select Edit Current Version | Log Adverse Event modal opens showing data just entered | Pass | BM | 2025-07-30 15:56
Click Save Changes button | Form shows You must provide reason for making the change and Errors in form. Please resolve before submitting | Pass | BM | 2025-07-30 15:56
Select "Treating" from Action Taken dropdown menu | Form shows selected value | Pass | BM | 2025-07-30 15:56
Enter "We told the patient to take some pepto bismol" in Description field | Form shows updated field | Pass | BM | 2025-07-30 15:56
Select "The Patient was excluded from the trial due to this event" | Check box selected | Pass | BM | 2025-07-30 15:56
Enter "Updated action taken" in Change Reason field | Form shows updated field | Pass | BM | 2025-07-30 15:56
Enter Password | Asterisks displayed | Pass | BM | 2025-07-30 15:56
Click Save Changes | Modal closes | Pass | BM | 2025-07-30 15:56
Click the kebab menu and select View Version History | Adverse Events version history table displayed | Pass | BM | 2025-07-30 15:56
On the first row, click the kebab menu and select View | Adverse Event modal opens with updated data in read only mode | Pass | BM | 2025-07-30 15:56
Click Close | Modal closes | Pass | BM | 2025-07-30 15:56
PI role Adverse Events, Lock and Unlock
Logout | Log in screen displayed | Pass | BM | 2025-07-30 15:56
Log in as user with PI role privileges | Home screen displayed | Pass | BM | 2025-07-30 15:56
Find patient, click kebab menu and select Patient Record | Patient Adherence screen displayed | Pass | BM | 2025-07-30 15:56
Click Lock button | Lock patient modal opens | Pass | BM | 2025-07-30 15:56
Enter Password | Asterisks displayed | Pass | BM | 2025-07-30 15:56
Click Lock button | Form shows "You must confirm that the patient data can be locked" | Pass | BM | 2025-07-30 15:56
Select patient data can be locked acknowledgement | Check box selected | Pass
Click Lock button | Modal closes and Lock button updates to Unlock | Pass | BM | 2025-07-30 15:56
Click Home button | Home screen displayed and patient status shows LOCKED (patient should be in first row, but possible they are not) | Pass | BM | 2025-07-30 15:56
For same patient (status = LOCKED), click kebab menu and select Patient Record | Patient Adherence screen displayed with status: "LOCKED" | Pass | BM | 2025-07-30 15:56
Confirm you cannot edit the data for adverse events, call logs, medical history, patient profile, tablet or mask panels. | All panels have data editing disabled. | Pass
Click Unlock button | Unlock Patient modal opens | Pass | BM | 2025-07-30 15:56
Click Unlock button | Form shows Valid description required error message | Pass | BM | 2025-07-30 15:56
Enter "Unlock test" in Description field | Field populates | Pass | BM | 2025-07-30 15:56
Click Unlock button | Modal closes, unlock button changes to lock button | Pass | BM | 2025-07-30 15:56
Click Patient Profile side navigation | Patient Profile versions screen displayed and you can update the current profile | Pass | BM | 2025-07-30 15:56
Confirm first two rows have reasons Data Lock and Data Unlock: Unlock test | Table shows correct reasons | Pass | BM | 2025-07-30 15:56
Click Adverse Events side navigation | Adverse Events screen displayed. If the user had an adverse event then you will see a table allowing you to view adverse events. Otherwise you see a message indicating the user did not experience any adverse events. | Pass | BM | 2025-07-30 15:56
Click kebab menu and select Edit Current Version | Log Adverse Event modal opens showing data entered | Pass | BM | 2025-07-30 15:56
Confirm you can see the section titled "PI/Medical Monitor Reviewed" | PI/Medical Monitor Reviewed section present | Pass | BM | 2025-07-30 15:56
Select "Yes" from PI Notified dropdown menu | Form shows selected value | Pass | BM | 2025-07-30 15:56
Enter "I reviewed the adverse event" in PI Notes field | Form shows updated field | Pass | BM | 2025-07-30 15:56
Enter Password | Asterisks displayed | Pass | BM | 2025-07-30 15:56
Enter "PI Reviewed" in Change Reason field | Form shows updated field | Pass | BM | 2025-07-30 15:56
Click Save Changes | Modal closes | Pass | BM | 2025-07-30 15:56
Click kebab menu and select Edit Current Version | Log Adverse Event modal opens showing data entered | Pass | BM | 2025-07-30 15:56
Confirm PI/Medical Monitor Reviewed section is present | Data entered previously is available on the form | Pass | BM | 2025-07-30 15:56
Click cancel button | Modal closes | Pass | BM | 2025-07-30 15:56
Formulas:
Date = IF([Initials]<>"",Now(),"")

## Patient Support Requests
| Document Number | PRC-017
| Document Revision | 00
Pain Clinical Application and Web Portal Verification
Test Procedure | Expected Results | Pass/Fail | Initials | Date | Notes
Patient Support Request on Tablet
On home screen, click the Contact Support button in the bottom navigation menu | Contact Trial support screen is displayed. Submit button is (disabled). Issue Type field is blank. Description field is blank. | Pass | BM | 2025-07-30 15:56
Click on the Help icon | Help text for page is displayed | Pass | BM | 2025-07-30 15:56
Click Close Help icon | Help text for page is closed | Pass | BM | 2025-07-30 15:56
Review text in upper left hand corner | Text says "Contact Support" | Pass | BM | 2025-07-30 15:56
Select "Issue With Tablet" as issue type | Issue type dropdown set to "Issue With Tablet". Submit button (enabled) | Pass | BM | 2025-07-30 15:56
In the Description field enter "Contact Trial Support test" screen. | Text entered is displayed in the Description field in the same format it was entered. Submit button (enabled) | Pass | BM | 2025-07-30 15:56
Click the Submit button | Thanks for Contacting Trial Support screen displayed. Home button (enabled) | Pass | BM | 2025-07-30 15:56
Click the Home button | Home screen displayed | Pass | BM | 2025-07-30 15:56
Check for email message
Open your email client and check that email is sent indicating patient made a request. | Email arrives and inidicates patient made a support request | Pass | BM | 2025-07-30 15:56
Patient Support Request on Web Portal
On home screen, click the Support Requests tab | Support requests table displayed | Pass | BM | 2025-07-30 15:56
Find the Issue "Contact Trial Support test" | Status: Follow Up Required | Pass | BM | 2025-07-30 15:56
For the Issue "Contact Trial Support test", click kebab menu and select Log Follow Up Call | Log Call modal displayed with Issue Type (disabled), Support Request Date (disabled), Content (disabled), Patient Phone Number (disabled), Call Date (enabled), Status = Follow Up Required (enabled) and Call Details (enabled) | Pass | BM | 2025-07-30 15:56
Click Log Call button | Form shows Call details required message | Pass | BM | 2025-07-30 15:56
In Status, select Follow Up Open | Follow Up Open displayed | Pass | BM | 2025-07-30 15:56
Enter "Called and left a message" in Call Details text area | Text entered is displayed | Pass | BM | 2025-07-30 15:56
Enter password | Asterisks displayed | Pass | BM | 2025-07-30 15:56
Click Log Call | Modal closes and tablet updates to show new status "Follow Up Open" | Pass | BM | 2025-07-30 15:56
On the same issue, click kebab menu and select Log Follow Up Call | Log Call modal displayed with Issue Type (disabled), Support Request Date (disabled), Content (disabled), Patient Phone Number (disabled), Call Date (enabled), Status = Follow Up Open (enabled) and Call Details (enabled) | Pass | BM | 2025-07-30 15:56
In Status, select Closed Resolved | Closed Resolved displayed | Pass | BM | 2025-07-30 15:56
Enter "Patient picked up and said everything is okay" in Call Details text area | Text entered is displayed | Pass | BM | 2025-07-30 15:56
Enter password and Click Log Call | Modal closes and table updates to show new status "Closed Resolved" | Pass | BM | 2025-07-30 15:56
On the same issue, click kebab menu and select Patient Record | Patient Data displayed | Pass | BM | 2025-07-30 15:56
Click on Patient Call Logs side navigation | Patient Calls screen displayed with two calls listed | Pass | BM | 2025-07-30 15:56
Find row w/ Patient picked up and said everything is okay, click kebab menu, view version history. | Table has a single row w/ you address as the author and reason set to initial call log. | Pass | BM | 2025-07-30 15:56
Click kebab menu and select view | Read only modal shows call data. | Pass | BM | 2025-07-30 15:56
Click close button | Modal closes | Pass | BM | 2025-07-30 15:56
Click back button | View showing all logged calls | Pass | BM | 2025-07-30 15:56
Find row w/ Patient picked up and said everything is okay, click kebab menu, select edit current version | Modal opens allowing you to edit the date, reason, call details, w/ required password and set change reason to testing update call log | Pass | BM | 2025-07-30 15:56
Update call details to: Patient is fine. Enter password and change reason, click Save Changes. | Modal closes, we see two rows in table, first row call details sayd Patient is fine. | Pass | BM | 2025-07-30 15:56
Click new call button | Modal opens allowing you to reason, call details, w/ required password. | Pass | BM | 2025-07-30 15:56
Enter patient was not adhering to trial in call details, select support request, enter password and click save. | Modal closes, table updates to show new call in first row. There are three rows in the table. | Pass | BM | 2025-07-30 15:56
Formulas:
Date = IF([Initials]<>"",Now(),"")

## Tablet & Mask Reassignment
| Document Number | PRC-017
| Document Revision | 00
Pain Clinical Application and Web Portal Verification
Test Procedure | Expected Results | Pass/Fail | Initials | Date | Notes
Tablet Reassignment on Web Portal
On home screen, find patient, click kebab menu and select Patient Record | Patient Adherence screen displayed | Pass | BM | 2025-07-30 15:56
Click on Tablet side navigation | Reassign Patient to Tablet screen displayed | Pass | BM | 2025-07-30 15:56
Enter "Tablet reassignment test" in Reassignment Reason | Form shows Reassignment Reason | Pass | BM | 2025-07-30 15:56
Click Reassign button | Register Patient on Tablet screen displayed | Pass | BM | 2025-07-30 15:56
Tablet Reassignment on Tablet
Start app on tablet that is not currently assigned to a patient | Setup screen shows allowing you to register the tablet. | Pass | BM | 2025-07-30 15:56
Complete Register Tablet | Tablet registration succeeds | Pass | BM | 2025-07-30 15:56
Complete Register Patient using Register Patient code from web portal | Patient registration succeeds and home page loads to show patient data. The data should be the same as it was on previous tablet. | Pass | BM | 2025-07-30 15:56
Tablet Reassignment on Web Portal
Click Next button | Patient Tablet Reassignment Successful modal displayed | Pass | BM | 2025-07-30 15:56
Click Close button | Reassign Patient to Tablet screen displayed | Pass | BM | 2025-07-30 15:56
Mask Reassignment on Web Portal
Click on Mask on side navigation | Current Patient/Mask Assignment screen displayed | Pass | BM | 2025-07-30 15:56
Enter "Mask reassignment test" in Mask Reassignment Reason. Do not select the checkbox underneath the textarea. | Form shows Mask Reassignment Reason | Pass | BM | 2025-07-30 15:56
Click Reassign button | Patient Tablet Reassignment Successful! displayed | Pass | BM | 2025-07-30 15:56
Mask Reassignment on Tablet
Open App | Home screen displayed | Pass | BM | 2025-07-30 15:56
Click on the Settings button | Setting page is displayed. Sync data button (enabled). Register Mask button (disabled). | Pass | BM | 2025-07-30 15:56
Click Sync Data button | Setting page is displayed. Sync data button (enabled). Register Mask button (enabled). | Pass | BM | 2025-07-30 15:56
Click Register Mask | Register mask Step 1 screen displayed | Pass | BM | 2025-07-30 15:56
Click Next button | Select mask Step 2 screen displayed | Pass | BM | 2025-07-30 15:56
Pickup available mask to be assigned and turn power switch to on
Select the mask from the list of available masks | Next button (enabled) | Pass | BM | 2025-07-30 15:56
Click on the Next button | Display screen Pairing Mask With Tablet and Mask Registration Complete when done pairing. Done button (enabled) | Pass | BM | 2025-07-30 15:56
Click the Done button | Home screen displayed | Pass | BM | 2025-07-30 15:56
Mask Reassignment on Web Portal
Click Sync Mask button | Patient Mask Reassignment Successful modal displayed | Pass | BM | 2025-07-30 15:56
Click Close button | Current Patient/Mask Assignment screen displayed | Pass | BM | 2025-07-30 15:56
Mask Reassignment on Web Portal with selecting Starting Phase 2 checkbox
Click on Mask on side navigation | Current Patient/Mask Assignment screen displayed | Pass | BM | 2025-07-30 15:56
Enter "Mask reassignment test" in Mask Reassignment Reason | Form shows Mask Reassignment Reason | Pass | BM | 2025-07-30 15:56
Select the checkbox underneath the textarea to indicate the patient is starting phase 2. | Checkbox selected | Pass | BM | 2025-07-30 15:56
Click Reassign button | Patient Tablet Reassignment Successful! displayed | Pass | BM | 2025-07-30 15:56
Mask Reassignment on Tablet
Open App | Home screen displayed | Pass | BM | 2025-07-30 15:56
Click on the Settings button | Setting page is displayed. Sync data button (enabled). Register Mask button (disabled). | Pass | BM | 2025-07-30 15:56
Click Sync Data button | Setting page is displayed. Sync data button (enabled). Register Mask button (enabled). | Pass | BM | 2025-07-30 15:56
Click Register Mask | Register mask Step 1 screen displayed | Pass | BM | 2025-07-30 15:56
Click Next button | Select mask Step 2 screen displayed | Pass | BM | 2025-07-30 15:56
Pickup available mask to be assigned and turn power switch to on
Select the mask from the list of available masks | Next button (enabled) | Pass | BM | 2025-07-30 15:56
Click on the Next button | Display screen Pairing Mask With Tablet and Mask Registration Complete when done pairing. Done button (enabled) | Pass | BM | 2025-07-30 15:56
Click the Done button | Home screen displayed | Pass | BM | 2025-07-30 15:56
Ensure the tablet is set to Phase 2 by checking that the evening log asks the medical usage questions | Evening logs asks medical usage questions | Pass | BM | 2025-07-30 15:56
Survey Reminders and Surveys
On tablet to 22 days from now
Load home screen | Suvery remiders appear | Pass | BM | 2025-07-30 15:56
On tablet to 24 days from now
Load home screen | Surveys active | Pass | BM | 2025-07-30 15:56
On tablet to 50 days from now
Load home screen | Suvery remiders appear | Pass | BM | 2025-07-30 15:56
On tablet to 52 days from now
Load home screen | Surveys active | Pass | BM | 2025-07-30 15:56
On tablet to 78 days from now
Load home screen | Suvery remiders appear | Pass | BM | 2025-07-30 15:56
On tablet to 80 days from now
Load home screen | Surveys active | Pass | BM | 2025-07-30 15:56
On tablet to 106 days from now
Load home screen | Suvery remiders appear | Pass | BM | 2025-07-30 15:56
On tablet to 108 days from now
Load home screen | Surveys active | Pass | BM | 2025-07-30 15:56
Mask Reassignment on Web Portal
Click Sync Mask button | Patient Mask Reassignment Successful modal displayed | Pass | BM | 2025-07-30 15:56
Click Close button | Current Patient/Mask Assignment screen displayed | Pass | BM | 2025-07-30 15:56
Formulas:
Date = IF([Initials]<>"",Now(),"")